## Project_Requests
project_id | project_name | project_type | location | green_area_sqft | rootzone_depth_in | drainage_pipe_lf | bunker_area_sqft | irrigation_pipe_lf | sod_area_sqft | earthwork_cy | site_access | target_duration_days | notes
GC-1001 | Cedar Ridge Practice Green Renovation | putting_green_renovation | North Texas | 8500 | 12 | 1250 | 0 | 900 | 12000 | 420 | good | 15 | Replace putting surface and rootzone; install drainage and irrigation improvements.
GC-1002 | Oak Hollow Bunker Rebuild | bunker_renovation | North Texas | 0 | 0 | 780 | 6200 | 180 | 2400 | 310 | moderate | 10 | Rebuild bunker shape, drainage, liner, sand, and surrounding turf.
GC-1003 | Prairie Run Irrigation Upgrade | irrigation_renovation | Central Texas | 0 | 0 | 0 | 0 | 6800 | 3500 | 950 | constrained | 20 | Replace selected irrigation mainlines and laterals; restore disturbed turf.
GC-1004 | Bluebonnet New Green Construction | new_putting_green | North Texas | 11000 | 12 | 1600 | 1800 | 1200 | 16000 | 700 | good | 25 | Construct new green with rootzone, drainage, irrigation, bunker, and sod tie-ins.
GC-1005 | Lakeside Tee Complex Refresh | tee_renovation | East Texas | 0 | 6 | 420 | 0 | 650 | 18500 | 260 | moderate | 12 | Regrade tees, amend growing medium, improve drainage, and install sod.
GC-1006 | Meadow Creek Fairway Grassing | fairway_grassing | Texas | 0 | 0 | 0 | 0 | 1200 | 42000 | 650 | good | 18 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1007 | River Bend Drainage Renewal | drainage_renovation | Texas | 0 | 0 | 4200 | 0 | 0 | 2400 | 1200 | moderate | 16 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1008 | Coyote Run New Green | new_putting_green | Texas | 12500 | 12 | 1850 | 950 | 1300 | 18500 | 980 | good | 28 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1009 | Willow Springs Bunker Package | bunker_renovation | Texas | 0 | 0 | 940 | 7400 | 240 | 3500 | 460 | constrained | 14 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1010 | Lone Star Irrigation Phase 2 | irrigation_renovation | Texas | 0 | 0 | 0 | 0 |  | 6200 | 1450 | moderate | 24 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1011 | Red Oak Tee Renovation | tee_renovation | Texas | 14500 | 6 | 460 | 0 | 720 | 21000 | 300 | good | 13 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1012 | Blue Heron Green Drainage | putting_green_renovation | Texas | 9600 | 12 | 1420 | 0 | 450 | 14500 | 580 | moderate | 18 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1013 | Pecan Grove Fairway Restoration | fairway_grassing | Texas | 0 | 0 | 0 | 0 | 650 | 55000 | 1250 | constrained | 22 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1014 | Stonebridge Drainage and Sod | drainage_renovation | Texas | 0 | 0 | 5200 | 0 | 0 | 7200 | 1550 | moderate | 20 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1015 | Cottonwood Practice Green | new_putting_green | Texas |  | 12 | 1180 | 1200 | 980 | 13500 | 760 | good | 23 | Synthetic test request; verify dimensions and specifications before final bid.
GC-1016

## Material_Catalog
material_id | material_name | unit | unit_cost_usd | waste_factor | category
MAT-001 | USGA rootzone mix | bulk_cy | 118 | 0.08 | green_construction
MAT-002 | Drainage gravel | ton | 46.5 | 0.07 | drainage
MAT-003 | Perforated HDPE drainage pipe, 4 in | lf | 2.85 | 0.05 | drainage
MAT-004 | PVC irrigation pipe, 4 in | lf | 5.6 | 0.05 | irrigation
MAT-005 | PVC irrigation pipe, 2 in | lf | 2.35 | 0.05 | irrigation
MAT-006 | Golf course sprinkler head | each | 185 | 0.03 | irrigation
MAT-007 | Bunker liner | sqft | 1.85 | 0.08 | bunker
MAT-008 | Washed bunker sand | ton | 52 | 0.08 | bunker
MAT-009 | Bermudagrass sod | sqft | 0.48 | 0.07 | turf
MAT-010 | Bermudagrass sprigs | acre | 1450 | 0.1 | turf
MAT-011 | Topsoil blend | bulk_cy | 39 | 0.08 | earthwork
MAT-012 | Geotextile fabric | sqft | 0.42 | 0.05 | drainage
MAT-013 | Pipe fittings and connectors allowance | allowance | 650 | 0 | irrigation
MAT-014 | Seed and establishment materials | acre | 780 | 0.1 | turf
MAT-015 | Bunker drainage stone | ton | 49 | 0.07 | bunker

## Equipment_Rates
equipment_id | equipment_name | rental_unit | daily_rate_usd | typical_use
EQ-001 | Excavator | day | 780 | earthwork/drainage
EQ-002 | Skid steer | day | 360 | site prep/turf
EQ-003 | Dump truck | day | 520 | hauling
EQ-004 | Trencher | day | 440 | irrigation/drainage
EQ-005 | Roller/compactor | day | 195 | grading

## Historical_Projects
history_id | project_type | primary_area_sqft_or_pipe_lf | final_cost_usd | average_crew_size | planned_duration_days | actual_duration_days | region | notes | green_or_tee_area_sqft | rootzone_depth_in | drainage_pipe_lf | irrigation_pipe_lf | bunker_area_sqft | sod_area_sqft | earthwork_cy | site_access | contingency_pct | overhead_profit_markup_pct | weather_delay_days | data_quality
HIST-0001 | irrigation_renovation | 6065 | 102007.41 | 10 | 16 | 20 | Oklahoma | Completed with minor quantity adjustments. | 0 | 0 | 0 | 6065 | 0 | 673 | 1326 | moderate | 0.125 | 0.12 | 4 | complete
HIST-0002 | tee_renovation | 19246 | 74384.39 | 7 | 13 | 12 | Central Texas | Minor weather delay; scope completed. | 19246 | 12 | 155 | 226 | 0 | 27321 | 257 | moderate | 0.125 | 0.18 | 0 | complete
HIST-0003 | putting_green_renovation | 6696 | 115433.42 | 7 | 18 | 22 | East Texas | Crew productivity was near plan. | 6696 | 12 | 1301 | 2009 | 869 | 16014 | 500 | moderate | 0.1 | 0.2 | 4 | complete
HIST-0004 | tee_renovation | 21872 | 91861.92 | 5 | 7 | 5 | East Texas | Scope change approved during construction. | 21872 | 12 | 471 | 680 | 0 | 20219 | 304 | constrained | 0.075 | 0.18 | 0 | complete
HIST-0005 | bunker_renovation | 996 | 98646.61 | 8 | 15 | 18 | Arkansas | Minor weather delay; scope completed. | 0 | 0 | 0 | 0 | 8332 | 4651 | 509 | moderate | 0.1 | 0.12 | 3 | complete
HIST-0006 | fairway_grassing | 165890 | 133216.37 | 7 | 21 | 22 | Central Texas | Completed with standard site access. | 165890 | 6 | 0 | 0 | 0 | 39039 | 1082 | moderate | 0.125 | 0.2 | 1 | complete
HIST-0007 | tee_renovation | 10808 | 48432.82 | 5 | 14 | 20 | Arkansas | Minor weather delay; scope completed. | 10808 | 8 | 142 | 262 | 0 | 18408 | 209 | good | 0.125 | 0.18 | 6 | complete
HIST-0008 | tee_renovation | 8889 | 78622.05 | 8 | 8 | 8 | Central Texas | Utility coordination added schedule risk. | 8889 | 12 | 294 | 506 | 0 | 16910 | 419 | moderate | 0.15 | 0.1 | 0 | complete
HIST-0009 | putting_green_renovation | 5714 | 137145.69 | 10 | 21 | 23 | Arkansas | Completed with standard site access. | 5714 | 12 | 924 | 1747 | 1153 | 12169 | 679 | moderate | 0.075 | 0.2 | 2 | complete
HIST-0010 | fairway_grassing | 149504 | 114412.02 | 10 | 14 | 13 | Oklahoma | Minor weather delay; scope completed. | 149504 | 10 | 0 | 0 | 0 | 31761 | 1014 | moderate | 0.15 | 0.15 | 0 | complete
HIST-0011 | drainage_renovation | 1717 | 59899.37 | 8 | 22 | 25 | West Texas | Completed with standard site access. | 0 | 0 | 959 | 0 | 0 | 1709 | 481 | good | 0.15 | 0.12 | 3 | complete
HIST-0012 | fairway_grassing | 167565 | 141468.86 | 11 | 17 | 17 | West Texas | Completed with minor quantity adjustments. | 167565 | 12 | 0 | 0 | 0 | 17835 | 404 | moderate | 0.1 | 0.18 | 0 | complete
HIST-0013 | tee_renovation | 18849 | 77150.44 | 9 | 14 | 14 | Arkansas | Crew productivity was near plan. | 18849 | 12 | 166 | 436 | 0 | 25643 | 167 | good | 0.075 | 0.1 | 0 | complete
HIST-0014 | drainage_renovation | 2490 | 55028.52 | 11 | 8 | 9 | West Texas | Minor weather delay; scope completed. | 0 | 0 | 1817 | 0 | 0 | 3766 | 1568 | good | 0.15 | 0.12 | 1 | complete
HIST-0015 | drainage_renovation | 4836 | 61376.53 | 10 | 12 | 12 | East Texas | Utility coordination added schedule risk. | 0 | 0 | 1788 | 0 | 0 | 2059 | 353 | moderate | 0.15 | 0.18 | 0 | complete
HIST-0016 | irrigation_renovation | 3775 | 125381.08 | 6 | 17 | 21 | East Texas | Completed with standard site access. | 0 | 0 | 0 | 3775 | 0 | 4268 | 1483 | moderate | 0.15 | 0.18 | 4 | complete
HIST-0017 | new_putting_green | 15160 | 159993.3 | 9 | 20 | 22 | North Texas | Completed with standard site access. | 15160 | 12 | 1267 | 2036 | 798 | 22713 | 548 | good | 0.125 | 0.1 | 2 | complete
HIST-0018 | bunker_renovation | 457 | 47313.16 | 8 | 9 | 9 | Central Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 0 | 8819 | 3529 | 275 | good | 0.15 | 0.15 | 0 | complete
HIST-0019 | new_putting_green | 13577 | 186802.87 | 11 | 23 | 26 | North Texas | Additional hauling required due to site conditions. | 13577 | 12 | 685 | 1082 | 871 | 24670 | 906 | moderate | 0.125 | 0.2 | 3 | complete
HIST-0020 | putting_green_renovation | 11163 | 187444.93 | 9 | 21 | 26 | Central Texas | Crew productivity was near plan. | 11163 | 6 | 723 | 1606 | 830 | 12869 | 531 | constrained | 0.15 | 0.1 | 3 | complete
HIST-0021 | fairway_grassing | 219299 | 75020.43 | 7 | 10 | 13 | Central Texas | Additional hauling required due to site conditions. | 219299 | 12 | 0 | 0 | 0 | 28560 | 392 | moderate | 0.075 | 0.2 | 3 | complete
HIST-0022 | new_putting_green | 14057 | 229113.99 | 13 | 32 | 36 | Central Texas | Utility coordination added schedule risk. | 14057 | 12 | 642 | 1265 | 2167 | 8106 | 740 | constrained | 0.1 | 0.18 | 2 | complete
HIST-0023 | drainage_renovation | 5344 | 129657.68 | 6 | 18 | 21 | West Texas | Crew productivity was near plan. | 0 | 0 | 3104 | 0 | 0 | 5261 | 919 | moderate | 0.075 | 0.12 | 3 | complete
HIST-0024 | putting_green_renovation | 12584 | 119493.8 | 6 | 14 | 13 | Arkansas | Unexpected subsurface conditions increased effort. | 12584 | 10 | 611 | 1020 | 1742 | 17120 | 218 | moderate | 0.075 | 0.18 | 0 | minor_scope_gap
HIST-0025 | fairway_grassing | 120607 | 168836.89 | 8 | 23 | 24 | East Texas | Crew productivity was near plan. | 120607 | 12 | 0 | 0 | 0 | 26584 | 1598 | good | 0.1 | 0.18 | 1 | complete
HIST-0026 | tee_renovation | 17426 | 50522.58 | 9 | 15 | 15 | Arkansas | Unexpected subsurface conditions increased effort. | 17426 | 12 | 405 | 553 | 0 | 16605 | 329 | moderate | 0.075 | 0.1 | 0 | complete
HIST-0027 | bunker_renovation | 848 | 103030.34 | 10 | 7 | 10 | Oklahoma | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 10260 | 2014 | 486 | moderate | 0.125 | 0.1 | 3 | complete
HIST-0028 | irrigation_renovation | 4177 | 151709.74 | 8 | 20 | 20 | North Texas | Utility coordination added schedule risk. | 0 | 0 | 0 | 4177 | 0 | 5621 | 1125 | moderate | 0.15 | 0.18 | 0 | complete
HIST-0029 | putting_green_renovation | 5724 | 84955.09 | 11 | 11 | 11 | East Texas | Material delivery timing affected productivity. | 5724 | 6 | 1147 | 1790 | 1675 | 16195 | 221 | good | 0.1 | 0.2 | 0 | complete
HIST-0030 | putting_green_renovation | 7839 | 136119.68 | 12 | 21 | 25 | Central Texas | Final quantities reconciled against field measurements. | 7839 | 12 | 688 | 927 | 1678 | 20303 | 885 | good | 0.125 | 0.1 | 4 | complete
HIST-0031 | putting_green_renovation | 5683 | 98434.87 | 12 | 15 | 21 | East Texas | Crew productivity was near plan. | 5683 | 12 | 1308 | 1754 | 1260 | 17505 | 863 | constrained | 0.15 | 0.2 | 4 | complete
HIST-0032 | putting_green_renovation | 13399 | 91759.82 | 6 | 16 | 22 | Oklahoma | Final quantities reconciled against field measurements. | 13399 | 12 | 902 | 1229 | 408 | 11827 | 751 | moderate | 0.075 | 0.15 | 6 | complete
HIST-0033 | putting_green_renovation | 9246 | 145787.35 | 8 | 23 | 23 | North Texas | Scope change approved during construction. | 9246 | 12 | 934 | 1638 | 1162 | 14097 | 321 | moderate | 0.1 | 0.15 | 0 | complete
HIST-0034 | bunker_renovation | 1190 | 84481.4 | 6 | 14 | 15 | Central Texas | Crew productivity was near plan. | 0 | 0 | 0 | 0 | 6867 | 3176 | 312 | good | 0.125 | 0.1 | 1 | complete
HIST-0035 | bunker_renovation | 579 | 83833.94 | 6 | 7 | 7 | East Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 8339 | 4970 | 334 | good | 0.1 | 0.12 | 0 | minor_scope_gap
HIST-0036 | new_putting_green | 7817 | 216773.9 | 8 | 26 | 27 | West Texas | Completed with standard site access. | 7817 | 12 | 619 | 1299 | 2211 | 26610 | 856 | moderate | 0.125 | 0.18 | 1 | complete
HIST-0037 | new_putting_green | 10890 | 202217.65 | 10 | 18 | 17 | Oklahoma | Unexpected subsurface conditions increased effort. | 10890 | 6 | 1028 | 2477 | 864 | 16581 | 1161 | good | 0.1 | 0.2 | 0 | complete
HIST-0038 | drainage_renovation | 1202 | 118243.02 | 12 | 13 | 13 | Arkansas | Final quantities reconciled against field measurements. | 0 | 0 | 774 | 0 | 0 | 4631 | 1510 | moderate | 0.1 | 0.12 | 0 | complete
HIST-0039 | new_putting_green | 13964 | 215118.88 | 8 | 24 | 26 | Central Texas | Scope change approved during construction. | 13964 | 10 | 1216 | 1485 | 3018 | 10625 | 866 | constrained | 0.1 | 0.12 | 0 | complete
HIST-0040 | irrigation_renovation | 3688 | 74194.94 | 9 | 21 | 27 | Arkansas | Minor weather delay; scope completed. | 0 | 0 | 0 | 3688 | 0 | 7051 | 1041 | moderate | 0.15 | 0.15 | 6 | complete
HIST-0041 | bunker_renovation | 492 | 113603.77 | 9 | 8 | 7 | Central Texas | Crew productivity was near plan. | 0 | 0 | 0 | 0 | 6673 | 2344 | 563 | good | 0.05 | 0.2 | 0 | complete
HIST-0042 | new_putting_green | 7136 | 182358.18 | 15 | 26 | 26 | East Texas | Final quantities reconciled against field measurements. | 7136 | 8 | 1170 | 1564 | 2118 | 14614 | 619 | good | 0.15 | 0.2 | 0 | complete
HIST-0043 | fairway_grassing | 213606 | 111932.56 | 12 | 14 | 20 | East Texas | Additional hauling required due to site conditions. | 213606 | 12 | 0 | 0 | 0 | 20840 | 1457 | good | 0.075 | 0.1 | 6 | complete
HIST-0044 | bunker_renovation | 389 | 54406.4 | 6 | 14 | 16 | North Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 5994 | 1996 | 374 | moderate | 0.05 | 0.18 | 2 | complete
HIST-0045 | putting_green_renovation | 10133 | 101619.59 | 8 | 14 | 17 | East Texas | Utility coordination added schedule risk. | 10133 | 12 | 1301 | 1630 | 1371 | 10411 | 242 | good | 0.125 | 0.12 | 3 | complete
HIST-0046 | drainage_renovation | 1172 | 108763.36 | 11 | 8 | 6 | Arkansas | Completed with minor quantity adjustments. | 0 | 0 | 801 | 0 | 0 | 2449 | 729 | good | 0.1 | 0.12 | 0 | minor_scope_gap
HIST-0047 | tee_renovation | 20801 | 62225.47 | 7 | 11 | 13 | West Texas | Utility coordination added schedule risk. | 20801 | 12 | 376 | 493 | 0 | 20231 | 273 | good | 0.15 | 0.2 | 2 | complete
HIST-0048 | fairway_grassing | 192108 | 146308.79 | 16 | 9 | 10 | Oklahoma | Unexpected subsurface conditions increased effort. | 192108 | 12 | 0 | 0 | 0 | 52564 | 839 | good | 0.15 | 0.12 | 1 | complete
HIST-0049 | fairway_grassing | 62724 | 148330.01 | 10 | 25 | 27 | West Texas | Unexpected subsurface conditions increased effort. | 62724 | 8 | 0 | 0 | 0 | 59215 | 642 | good | 0.05 | 0.18 | 2 | complete
HIST-0050 | putting_green_renovation | 6998 | 183585.16 | 11 | 11 | 11 | Arkansas | Crew productivity was near plan. | 6998 | 12 | 632 | 1013 | 1669 | 9868 | 262 | constrained | 0.05 | 0.15 | 0 | complete
HIST-0051 | bunker_renovation | 635 | 55640.38 | 9 | 15 | 16 | Oklahoma | Material delivery timing affected productivity. | 0 | 0 | 0 | 0 | 9510 | 1307 | 451 | constrained | 0.1 | 0.1 | 0 | complete
HIST-0052 | new_putting_green | 15001 | 252716.12 | 11 | 27 | 27 | Arkansas | Utility coordination added schedule risk. | 15001 | 12 | 504 | 987 | 1170 | 22182 | 472 | moderate | 0.05 | 0.18 | 0 | complete
HIST-0053 | irrigation_renovation | 6324 | 80419.66 | 8 | 24 | 25 | Central Texas | Scope change approved during construction. | 0 | 0 | 0 | 6324 | 0 | 3555 | 569 | moderate | 0.15 | 0.2 | 1 | complete
HIST-0054 | putting_green_renovation | 10129 | 100323.76 | 8 | 17 | 13 | Arkansas | Utility coordination added schedule risk. | 10129 | 12 | 423 | 680 | 24 | 17622 | 868 | good | 0.15 | 0.15 | 0 | complete
HIST-0055 | putting_green_renovation | 8134 | 124141.38 | 12 | 15 | 14 | North Texas | Additional hauling required due to site conditions. | 8134 | 12 | 831 | 1504 | 622 | 7534 | 748 | moderate | 0.125 | 0.2 | 0 | minor_scope_gap
HIST-0056 | drainage_renovation | 2031 | 128457.2 | 8 | 14 | 14 | Oklahoma | Scope change approved during construction. | 0 | 0 | 994 | 0 | 0 | 1282 | 1460 | moderate | 0.05 | 0.1 | 0 | complete
HIST-0057 | irrigation_renovation | 6178 | 84992.49 | 12 | 10 | 11 | Central Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 6178 | 0 | 7614 | 719 | moderate | 0.125 | 0.15 | 1 | complete
HIST-0058 | irrigation_renovation | 6773 | 126537.67 | 8 | 15 | 15 | East Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 6773 | 0 | 5165 | 306 | moderate | 0.05 | 0.1 | 0 | complete
HIST-0059 | fairway_grassing | 63793 | 71522.12 | 8 | 15 | 19 | Central Texas | Minor weather delay; scope completed. | 63793 | 12 | 0 | 0 | 0 | 18380 | 418 | good | 0.15 | 0.12 | 4 | complete
HIST-0060 | putting_green_renovation | 10792 | 161481.85 | 9 | 20 | 22 | West Texas | Unexpected subsurface conditions increased effort. | 10792 | 12 | 332 | 677 | 1035 | 6177 | 788 | good | 0.1 | 0.15 | 2 | complete
HIST-0061 | bunker_renovation | 329 | 98609.05 | 9 | 8 | 8 | East Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 4720 | 4345 | 116 | good | 0.075 | 0.15 | 0 | complete
HIST-0062 | irrigation_renovation | 2965 | 108212.45 | 11 | 22 | 24 | East Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 2965 | 0 | 5946 | 740 | good | 0.1 | 0.1 | 2 | complete
HIST-0063 | putting_green_renovation | 7831 | 87030.73 | 6 | 18 | 17 | North Texas | Scope change approved during construction. | 7831 | 10 | 592 | 951 | 1142 | 17761 | 570 | moderate | 0.075 | 0.15 | 0 | complete
HIST-0064 | drainage_renovation | 4602 | 93637.4 | 8 | 15 | 21 | East Texas | Material delivery timing affected productivity. | 0 | 0 | 2006 | 0 | 0 | 8077 | 488 | good | 0.075 | 0.12 | 6 | complete
HIST-0065 | irrigation_renovation | 10468 | 153756.72 | 13 | 26 | 25 | West Texas | Completed with standard site access. | 0 | 0 | 0 | 10468 | 0 | 7029 | 533 | moderate | 0.1 | 0.18 | 0 | complete
HIST-0066 | new_putting_green | 11289 | 244514.48 | 12 | 29 | 31 | West Texas | Additional hauling required due to site conditions. | 11289 | 12 | 1168 | 1671 | 2751 | 11012 | 973 | good | 0.125 | 0.1 | 2 | complete
HIST-0067 | new_putting_green | 10298 | 242970.15 | 15 | 25 | 26 | Oklahoma | Material delivery timing affected productivity. | 10298 | 8 | 1569 | 2424 | 863 | 14331 | 857 | moderate | 0.125 | 0.18 | 1 | complete
HIST-0068 | bunker_renovation | 1066 | 70250.03 | 8 | 8 | 14 | Oklahoma | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 8732 | 2628 | 417 | moderate | 0.05 | 0.18 | 6 | complete
HIST-0069 | drainage_renovation | 3499 | 106707.26 | 7 | 10 | 16 | Oklahoma | Completed with minor quantity adjustments. | 0 | 0 | 1960 | 0 | 0 | 4553 | 943 | constrained | 0.05 | 0.2 | 4 | complete
HIST-0070 | tee_renovation | 25613 | 68028.59 | 5 | 9 | 10 | West Texas | Material delivery timing affected productivity. | 25613 | 10 | 440 | 597 | 0 | 16089 | 132 | good | 0.1 | 0.18 | 1 | complete
HIST-0071 | fairway_grassing | 118159 | 65546.42 | 8 | 17 | 17 | Arkansas | Additional hauling required due to site conditions. | 118159 | 12 | 0 | 0 | 0 | 63735 | 1748 | good | 0.075 | 0.2 | 0 | complete
HIST-0072 | tee_renovation | 14506 | 44282.58 | 9 | 6 | 7 | West Texas | Scope change approved during construction. | 14506 | 12 | 463 | 746 | 0 | 25538 | 216 | moderate | 0.075 | 0.15 | 1 | complete
HIST-0073 | bunker_renovation | 744 | 55312.76 | 10 | 12 | 9 | Oklahoma | Material delivery timing affected productivity. | 0 | 0 | 0 | 0 | 4654 | 1278 | 173 | good | 0.125 | 0.2 | 0 | complete
HIST-0074 | irrigation_renovation | 6906 | 121169.99 | 13 | 23 | 25 | East Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 6906 | 0 | 2161 | 915 | good | 0.125 | 0.1 | 2 | complete
HIST-0075 | drainage_renovation | 4572 | 103581.35 | 6 | 16 | 18 | Arkansas | Final quantities reconciled against field measurements. | 0 | 0 | 2891 | 0 | 0 | 1456 | 327 | moderate | 0.05 | 0.15 | 2 | complete
HIST-0076 | tee_renovation | 9795 | 88695.44 | 5 | 14 | 15 | West Texas | Utility coordination added schedule risk. | 9795 | 8 | 329 | 461 | 0 | 18992 | 125 | moderate | 0.075 | 0.2 | 1 | complete
HIST-0077 | irrigation_renovation | 4333 | 72923.08 | 12 | 28 | 29 | East Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 4333 | 0 | 4225 | 1127 | good | 0.1 | 0.1 | 1 | complete
HIST-0078 | bunker_renovation | 1141 | 99239.3 | 6 | 10 | 11 | Arkansas | Utility coordination added schedule risk. | 0 | 0 | 0 | 0 | 6408 | 5762 | 319 | moderate | 0.1 | 0.2 | 1 | complete
HIST-0079 | irrigation_renovation | 2479 | 157143.14 | 7 | 19 | 22 | East Texas | Utility coordination added schedule risk. | 0 | 0 | 0 | 2479 | 0 | 3907 | 1064 | constrained | 0.1 | 0.15 | 1 | complete
HIST-0080 | drainage_renovation | 2544 | 61925.51 | 12 | 16 | 16 | North Texas | Utility coordination added schedule risk. | 0 | 0 | 1545 | 0 | 0 | 8545 | 1053 | good | 0.075 | 0.18 | 0 | minor_scope_gap
HIST-0081 | irrigation_renovation | 9791 | 95309.1 | 7 | 13 | 15 | West Texas | Crew productivity was near plan. | 0 | 0 | 0 | 9791 | 0 | 4302 | 1350 | good | 0.1 | 0.15 | 2 | complete
HIST-0082 | bunker_renovation | 1188 | 96408.53 | 5 | 13 | 11 | North Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 0 | 6237 | 5682 | 589 | good | 0.125 | 0.2 | 0 | complete
HIST-0083 | new_putting_green | 10743 | 132372.98 | 13 | 30 | 30 | North Texas | Completed with standard site access. | 10743 | 12 | 745 | 1531 | 1718 | 19687 | 1006 | good | 0.05 | 0.1 | 0 | complete
HIST-0084 | putting_green_renovation | 8092 | 122558.44 | 8 | 15 | 14 | West Texas | Final quantities reconciled against field measurements. | 8092 | 12 | 351 | 794 | 96 | 20841 | 454 | moderate | 0.125 | 0.2 | 0 | complete
HIST-0085 | irrigation_renovation | 9432 | 93169.63 | 11 | 15 | 16 | Arkansas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 9432 | 0 | 3769 | 440 | good | 0.075 | 0.18 | 1 | complete
HIST-0086 | irrigation_renovation | 10224 | 130140.16 | 10 | 20 | 20 | Oklahoma | Minor weather delay; scope completed. | 0 | 0 | 0 | 10224 | 0 | 5665 | 274 | moderate | 0.125 | 0.18 | 0 | complete
HIST-0087 | irrigation_renovation | 4431 | 63663.64 | 12 | 20 | 24 | Central Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 4431 | 0 | 5184 | 1720 | moderate | 0.075 | 0.18 | 4 | complete
HIST-0088 | drainage_renovation | 2484 | 107055.72 | 12 | 14 | 15 | Central Texas | Completed with standard site access. | 0 | 0 | 2078 | 0 | 0 | 1489 | 884 | good | 0.05 | 0.12 | 1 | complete
HIST-0089 | bunker_renovation | 430 | 119565 | 9 | 15 | 15 | West Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 6320 | 3698 | 580 | constrained | 0.05 | 0.1 | 0 | complete
HIST-0090 | tee_renovation | 20711 | 80337.08 | 4 | 15 | 16 | Arkansas | Completed with minor quantity adjustments. | 20711 | 6 | 219 | 373 | 0 | 16520 | 393 | good | 0.125 | 0.2 | 1 | complete
HIST-0091 | new_putting_green | 7633 | 154201.71 | 15 | 30 | 30 | East Texas | Final quantities reconciled against field measurements. | 7633 | 10 | 1044 | 2533 | 1817 | 14409 | 535 | good | 0.125 | 0.18 | 0 | complete
HIST-0092 | drainage_renovation | 2291 | 51393.45 | 7 | 16 | 18 | North Texas | Minor weather delay; scope completed. | 0 | 0 | 1941 | 0 | 0 | 1402 | 1249 | constrained | 0.05 | 0.1 | 0 | complete
HIST-0093 | tee_renovation | 23445 | 76773.92 | 7 | 11 | 12 | Arkansas | Additional hauling required due to site conditions. | 23445 | 12 | 112 | 256 | 0 | 20185 | 309 | good | 0.15 | 0.15 | 1 | complete
HIST-0094 | irrigation_renovation | 3850 | 157249.25 | 10 | 26 | 29 | North Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 3850 | 0 | 5304 | 1285 | constrained | 0.075 | 0.2 | 1 | complete
HIST-0095 | irrigation_renovation | 10354 | 89505.3 | 10 | 22 | 24 | West Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 10354 | 0 | 4860 | 1461 | moderate | 0.15 | 0.15 | 2 | complete
HIST-0096 | new_putting_green | 7574 | 197571.56 | 10 | 31 | 27 | North Texas | Utility coordination added schedule risk. | 7574 | 12 | 1450 | 2099 | 571 | 8350 | 460 | moderate | 0.125 | 0.18 | 0 | complete
HIST-0097 | tee_renovation | 9967 | 52882.07 | 5 | 11 | 11 | Oklahoma | Minor weather delay; scope completed. | 9967 | 12 | 327 | 577 | 0 | 17213 | 304 | moderate | 0.05 | 0.12 | 0 | complete
HIST-0098 | putting_green_renovation | 8254 | 111779.66 | 10 | 15 | 15 | Central Texas | Utility coordination added schedule risk. | 8254 | 12 | 500 | 1186 | 1252 | 20336 | 500 | good | 0.15 | 0.2 | 0 | complete
HIST-0099 | irrigation_renovation | 5802 | 133261.02 | 7 | 13 | 17 | Arkansas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 5802 | 0 | 1405 | 361 | moderate | 0.05 | 0.12 | 4 | complete
HIST-0100 | new_putting_green | 10131 | 219645.56 | 8 | 27 | 26 | Arkansas | Material delivery timing affected productivity. | 10131 | 8 | 701 | 983 | 436 | 21452 | 982 | moderate | 0.075 | 0.15 | 0 | complete
HIST-0101 | new_putting_green | 8927 | 197163.07 | 9 | 17 | 14 | North Texas | Scope change approved during construction. | 8927 | 10 | 897 | 2009 | 22 | 17766 | 668 | good | 0.15 | 0.18 | 0 | complete
HIST-0102 | drainage_renovation | 919 | 82254.88 | 10 | 9 | 15 | Oklahoma | Material delivery timing affected productivity. | 0 | 0 | 656 | 0 | 0 | 3796 | 1132 | good | 0.125 | 0.15 | 6 | complete
HIST-0103 | fairway_grassing | 152120 | 106409.77 | 9 | 14 | 16 | North Texas | Minor weather delay; scope completed. | 152120 | 12 | 0 | 0 | 0 | 64261 | 1729 | good | 0.05 | 0.18 | 2 | complete
HIST-0104 | tee_renovation | 23728 | 59518.32 | 7 | 12 | 11 | North Texas | Unexpected subsurface conditions increased effort. | 23728 | 8 | 307 | 414 | 0 | 13618 | 438 | moderate | 0.125 | 0.18 | 0 | complete
HIST-0105 | fairway_grassing | 192610 | 78356.32 | 11 | 23 | 24 | West Texas | Crew productivity was near plan. | 192610 | 12 | 0 | 0 | 0 | 25987 | 969 | constrained | 0.05 | 0.15 | 0 | complete
HIST-0106 | irrigation_renovation | 9835 | 78473.82 | 9 | 28 | 28 | East Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 9835 | 0 | 6320 | 504 | moderate | 0.1 | 0.12 | 0 | complete
HIST-0107 | tee_renovation | 8530 | 86713.97 | 5 | 14 | 11 | West Texas | Material delivery timing affected productivity. | 8530 | 10 | 504 | 827 | 0 | 27905 | 479 | moderate | 0.125 | 0.18 | 0 | complete
HIST-0108 | bunker_renovation | 870 | 90437.5 | 7 | 10 | 11 | Oklahoma | Scope change approved during construction. | 0 | 0 | 0 | 0 | 6175 | 3196 | 285 | good | 0.1 | 0.15 | 1 | complete
HIST-0109 | irrigation_renovation | 10280 | 134690.38 | 6 | 14 | 18 | North Texas | Completed with standard site access. | 0 | 0 | 0 | 10280 | 0 | 1159 | 576 | good | 0.15 | 0.2 | 4 | complete
HIST-0110 | tee_renovation | 21588 | 64436.84 | 7 | 6 | 10 | Arkansas | Completed with standard site access. | 21588 | 12 | 187 | 429 | 0 | 26815 | 223 | constrained | 0.125 | 0.2 | 2 | complete
HIST-0111 | drainage_renovation | 2008 | 55521.91 | 7 | 21 | 22 | Oklahoma | Utility coordination added schedule risk. | 0 | 0 | 1636 | 0 | 0 | 4526 | 1437 | good | 0.15 | 0.18 | 1 | complete
HIST-0112 | putting_green_renovation | 13068 | 112514.62 | 6 | 15 | 19 | Oklahoma | Unexpected subsurface conditions increased effort. | 13068 | 12 | 958 | 1294 | 737 | 9246 | 441 | good | 0.15 | 0.12 | 4 | complete
HIST-0113 | bunker_renovation | 725 | 74016.06 | 7 | 8 | 8 | Central Texas | Crew productivity was near plan. | 0 | 0 | 0 | 0 | 10454 | 4106 | 323 | good | 0.15 | 0.18 | 0 | complete
HIST-0114 | drainage_renovation | 1263 | 66526.27 | 9 | 16 | 16 | West Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 902 | 0 | 0 | 1891 | 756 | moderate | 0.05 | 0.1 | 0 | complete
HIST-0115 | tee_renovation | 9201 | 43265.63 | 5 | 9 | 8 | North Texas | Crew productivity was near plan. | 9201 | 8 | 415 | 694 | 0 | 13463 | 258 | good | 0.05 | 0.15 | 0 | minor_scope_gap
HIST-0116 | putting_green_renovation | 6437 | 101264.44 | 8 | 15 | 18 | Arkansas | Utility coordination added schedule risk. | 6437 | 12 | 1188 | 2056 | 126 | 21948 | 402 | moderate | 0.15 | 0.1 | 3 | complete
HIST-0117 | bunker_renovation | 793 | 71728.95 | 7 | 10 | 11 | East Texas | Minor weather delay; scope completed. | 0 | 0 | 0 | 0 | 4418 | 4960 | 115 | constrained | 0.05 | 0.1 | 0 | complete
HIST-0118 | irrigation_renovation | 7382 | 99521.95 | 9 | 16 | 16 | West Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 7382 | 0 | 4439 | 1795 | good | 0.125 | 0.1 | 0 | complete
HIST-0119 | irrigation_renovation | 3280 | 77230.38 | 6 | 22 | 23 | Oklahoma | Completed with standard site access. | 0 | 0 | 0 | 3280 | 0 | 5003 | 1180 | good | 0.05 | 0.12 | 1 | complete
HIST-0120 | irrigation_renovation | 2886 | 94385.97 | 9 | 14 | 13 | Oklahoma | Completed with standard site access. | 0 | 0 | 0 | 2886 | 0 | 1639 | 1354 | moderate | 0.125 | 0.2 | 0 | complete
HIST-0121 | putting_green_renovation | 7542 | 139956.81 | 12 | 22 | 22 | East Texas | Additional hauling required due to site conditions. | 7542 | 12 | 666 | 1146 | 312 | 9505 | 844 | good | 0.125 | 0.15 | 0 | complete
HIST-0122 | new_putting_green | 14774 | 164777.3 | 13 | 21 | 21 | Oklahoma | Additional hauling required due to site conditions. | 14774 | 12 | 902 | 1975 | 2086 | 18969 | 1188 | moderate | 0.075 | 0.2 | 0 | complete
HIST-0123 | putting_green_renovation | 6962 | 85606.36 | 12 | 14 | 20 | West Texas | Final quantities reconciled against field measurements. | 6962 | 12 | 1561 | 2038 | 206 | 10503 | 742 | moderate | 0.15 | 0.15 | 6 | complete
HIST-0124 | drainage_renovation | 2269 | 76212.49 | 10 | 12 | 14 | Central Texas | Completed with standard site access. | 0 | 0 | 1307 | 0 | 0 | 1058 | 955 | constrained | 0.05 | 0.15 | 0 | complete
HIST-0125 | bunker_renovation | 340 | 107555.27 | 7 | 10 | 10 | North Texas | Utility coordination added schedule risk. | 0 | 0 | 0 | 0 | 2775 | 4984 | 402 | good | 0.075 | 0.2 | 0 | complete
HIST-0126 | bunker_renovation | 404 | 54929.19 | 10 | 13 | 16 | East Texas | Minor weather delay; scope completed. | 0 | 0 | 0 | 0 | 8607 | 1353 | 158 | constrained | 0.15 | 0.15 | 1 | complete
HIST-0127 | putting_green_renovation | 12444 | 93808.92 | 11 | 14 | 14 | West Texas | Final quantities reconciled against field measurements. | 12444 | 10 | 1010 | 2076 | 665 | 15463 | 247 | moderate | 0.125 | 0.15 | 0 | complete
HIST-0128 | irrigation_renovation | 4456 | 154512.5 | 9 | 27 | 29 | East Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 4456 | 0 | 6417 | 1163 | constrained | 0.075 | 0.1 | 0 | complete
HIST-0129 | bunker_renovation | 425 | 108719.38 | 8 | 9 | 9 | Arkansas | Material delivery timing affected productivity. | 0 | 0 | 0 | 0 | 6490 | 5989 | 361 | good | 0.075 | 0.18 | 0 | complete
HIST-0130 | drainage_renovation | 4145 | 125537.79 | 5 | 9 | 9 | Central Texas | Utility coordination added schedule risk. | 0 | 0 | 2182 | 0 | 0 | 3444 | 697 | moderate | 0.125 | 0.12 | 0 | complete
HIST-0131 | putting_green_renovation | 11370 | 112828.82 | 12 | 16 | 17 | Oklahoma | Utility coordination added schedule risk. | 11370 | 10 | 1054 | 1634 | 407 | 13875 | 573 | good | 0.075 | 0.18 | 1 | complete
HIST-0132 | putting_green_renovation | 7475 | 163469.35 | 9 | 22 | 22 | Arkansas | Utility coordination added schedule risk. | 7475 | 8 | 886 | 1501 | 1513 | 19326 | 822 | moderate | 0.075 | 0.15 | 0 | complete
HIST-0133 | tee_renovation | 21073 | 57244.61 | 4 | 10 | 11 | West Texas | Final quantities reconciled against field measurements. | 21073 | 10 | 354 | 646 | 0 | 18375 | 512 | moderate | 0.125 | 0.18 | 1 | complete
HIST-0134 | tee_renovation | 16454 | 47574.77 | 7 | 13 | 13 | Arkansas | Final quantities reconciled against field measurements. | 16454 | 12 | 416 | 582 | 0 | 22002 | 303 | good | 0.15 | 0.12 | 0 | complete
HIST-0135 | fairway_grassing | 121307 | 137267.77 | 16 | 9 | 10 | North Texas | Final quantities reconciled against field measurements. | 121307 | 8 | 0 | 0 | 0 | 37432 | 954 | good | 0.15 | 0.15 | 1 | complete
HIST-0136 | irrigation_renovation | 4740 | 122456.3 | 7 | 10 | 14 | Central Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 4740 | 0 | 4599 | 1662 | good | 0.15 | 0.2 | 4 | complete
HIST-0137 | tee_renovation | 11553 | 70119 | 5 | 6 | 6 | North Texas | Material delivery timing affected productivity. | 11553 | 8 | 603 | 745 | 0 | 8981 | 546 | moderate | 0.1 | 0.1 | 0 | complete
HIST-0138 | fairway_grassing | 188936 | 121193.73 | 15 | 15 | 15 | North Texas | Minor weather delay; scope completed. | 188936 | 12 | 0 | 0 | 0 | 58677 | 1465 | moderate | 0.075 | 0.18 | 0 | complete
HIST-0139 | drainage_renovation | 1093 | 114819.13 | 11 | 13 | 17 | West Texas | Scope change approved during construction. | 0 | 0 | 386 | 0 | 0 | 3473 | 966 | constrained | 0.05 | 0.2 | 2 | complete
HIST-0140 | bunker_renovation | 1081 | 78980.13 | 10 | 9 | 10 | Central Texas | Completed with standard site access. | 0 | 0 | 0 | 0 | 5975 | 1783 | 334 | good | 0.05 | 0.18 | 1 | complete
HIST-0141 | drainage_renovation | 6428 | 92264.33 | 12 | 9 | 7 | Arkansas | Final quantities reconciled against field measurements. | 0 | 0 | 2670 | 0 | 0 | 8918 | 469 | good | 0.125 | 0.15 | 0 | complete
HIST-0142 | bunker_renovation | 966 | 64756.46 | 9 | 16 | 18 | Arkansas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 4680 | 1008 | 628 | moderate | 0.125 | 0.2 | 2 | complete
HIST-0143 | drainage_renovation | 1973 | 110710.47 | 9 | 13 | 14 | North Texas | Utility coordination added schedule risk. | 0 | 0 | 1403 | 0 | 0 | 7342 | 741 | good | 0.15 | 0.12 | 1 | complete
HIST-0144 | bunker_renovation | 844 | 83115.64 | 6 | 9 | 11 | West Texas | Crew productivity was near plan. | 0 | 0 | 0 | 0 | 6100 | 3999 | 159 | good | 0.05 | 0.12 | 2 | complete
HIST-0145 | putting_green_renovation | 10807 | 152930.77 | 10 | 22 | 28 | Oklahoma | Completed with standard site access. | 10807 | 6 | 932 | 1888 | 1409 | 19478 | 642 | moderate | 0.05 | 0.1 | 6 | complete
HIST-0146 | irrigation_renovation | 6760 | 131163.87 | 8 | 26 | 29 | East Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 6760 | 0 | 5309 | 348 | good | 0.075 | 0.1 | 3 | complete
HIST-0147 | new_putting_green | 12174 | 167209.4 | 9 | 27 | 28 | West Texas | Crew productivity was near plan. | 12174 | 12 | 1429 | 2321 | 2870 | 19814 | 494 | good | 0.125 | 0.18 | 1 | complete
HIST-0148 | putting_green_renovation | 6467 | 127411.46 | 7 | 21 | 26 | East Texas | Utility coordination added schedule risk. | 6467 | 6 | 1472 | 2009 | 195 | 13540 | 897 | constrained | 0.15 | 0.18 | 3 | complete
HIST-0149 | fairway_grassing | 125179 | 88486.63 | 8 | 8 | 10 | North Texas | Scope change approved during construction. | 125179 | 12 | 0 | 0 | 0 | 15328 | 361 | constrained | 0.15 | 0.1 | 0 | complete
HIST-0150 | irrigation_renovation | 9037 | 63523.49 | 7 | 16 | 22 | West Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 9037 | 0 | 2104 | 1319 | moderate | 0.1 | 0.18 | 6 | complete
HIST-0151 | new_putting_green | 13219 | 166466.42 | 10 | 18 | 19 | Central Texas | Utility coordination added schedule risk. | 13219 | 6 | 753 | 1394 | 3209 | 23670 | 401 | good | 0.075 | 0.12 | 1 | complete
HIST-0152 | drainage_renovation | 5405 | 106324.28 | 8 | 11 | 9 | West Texas | Material delivery timing affected productivity. | 0 | 0 | 3605 | 0 | 0 | 1703 | 1330 | moderate | 0.075 | 0.2 | 0 | complete
HIST-0153 | irrigation_renovation | 10433 | 66677.67 | 9 | 15 | 17 | East Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 10433 | 0 | 3661 | 1679 | good | 0.15 | 0.18 | 2 | complete
HIST-0154 | drainage_renovation | 5165 | 123789.66 | 8 | 9 | 10 | Arkansas | Scope change approved during construction. | 0 | 0 | 2997 | 0 | 0 | 7382 | 915 | good | 0.15 | 0.18 | 1 | complete
HIST-0155 | irrigation_renovation | 2936 | 60779.98 | 13 | 20 | 19 | West Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 2936 | 0 | 1906 | 751 | good | 0.125 | 0.12 | 0 | complete
HIST-0156 | irrigation_renovation | 4686 | 97128.92 | 7 | 26 | 24 | Arkansas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 4686 | 0 | 4918 | 770 | moderate | 0.125 | 0.15 | 0 | complete
HIST-0157 | putting_green_renovation | 10807 | 88735.06 | 9 | 17 | 17 | Oklahoma | Crew productivity was near plan. | 10807 | 8 | 814 | 1166 | 213 | 14371 | 818 | good | 0.05 | 0.12 | 0 | complete
HIST-0158 | irrigation_renovation | 2010 | 82398.42 | 10 | 12 | 10 | Oklahoma | Completed with minor quantity adjustments. | 0 | 0 | 0 | 2010 | 0 | 6627 | 1465 | moderate | 0.075 | 0.1 | 0 | complete
HIST-0159 | tee_renovation | 10233 | 105286.97 | 9 | 7 | 11 | North Texas | Scope change approved during construction. | 10233 | 6 | 205 | 337 | 0 | 24547 | 278 | constrained | 0.075 | 0.1 | 2 | complete
HIST-0160 | drainage_renovation | 5020 | 109428.97 | 11 | 17 | 21 | West Texas | Minor weather delay; scope completed. | 0 | 0 | 3740 | 0 | 0 | 7896 | 1032 | good | 0.075 | 0.1 | 4 | complete
HIST-0161 | fairway_grassing | 88525 | 97136.18 | 14 | 22 | 22 | East Texas | Minor weather delay; scope completed. | 88525 | 8 | 0 | 0 | 0 | 56233 | 1531 | moderate | 0.075 | 0.1 | 0 | complete
HIST-0162 | fairway_grassing | 139629 | 161433.28 | 11 | 11 | 8 | Oklahoma | Unexpected subsurface conditions increased effort. | 139629 | 12 | 0 | 0 | 0 | 22051 | 1090 | good | 0.15 | 0.1 | 0 | complete
HIST-0163 | putting_green_renovation | 6096 | 102522.07 | 9 | 21 | 20 | North Texas | Utility coordination added schedule risk. | 6096 | 8 | 551 | 764 | 1667 | 9786 | 719 | good | 0.075 | 0.1 | 0 | complete
HIST-0164 | fairway_grassing | 85591 | 100287.14 | 10 | 12 | 14 | East Texas | Material delivery timing affected productivity. | 85591 | 12 | 0 | 0 | 0 | 49110 | 975 | moderate | 0.125 | 0.2 | 2 | complete
HIST-0165 | fairway_grassing | 160861 | 152041.06 | 10 | 15 | 18 | Arkansas | Scope change approved during construction. | 160861 | 8 | 0 | 0 | 0 | 56987 | 1038 | good | 0.075 | 0.2 | 3 | complete
HIST-0166 | drainage_renovation | 4511 | 86915.24 | 9 | 9 | 9 | Oklahoma | Final quantities reconciled against field measurements. | 0 | 0 | 1815 | 0 | 0 | 4389 | 880 | good | 0.15 | 0.2 | 0 | complete
HIST-0167 | irrigation_renovation | 5896 | 113708.49 | 6 | 24 | 23 | West Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 5896 | 0 | 6620 | 903 | good | 0.075 | 0.12 | 0 | complete
HIST-0168 | fairway_grassing | 96613 | 83680.98 | 10 | 20 | 19 | Central Texas | Unexpected subsurface conditions increased effort. | 96613 | 12 | 0 | 0 | 0 | 48238 | 1586 | constrained | 0.15 | 0.15 | 0 | complete
HIST-0169 | fairway_grassing | 83532 | 78810.89 | 10 | 14 | 15 | Arkansas | Unexpected subsurface conditions increased effort. | 83532 | 12 | 0 | 0 | 0 | 20203 | 707 | good | 0.075 | 0.12 | 1 | complete
HIST-0170 | new_putting_green | 7312 | 149998.79 | 14 | 22 | 18 | East Texas | Completed with standard site access. | 7312 | 12 | 932 | 1537 | 3254 | 21266 | 463 | good | 0.15 | 0.2 | 0 | complete
HIST-0171 | putting_green_renovation | 8411 | 144028.93 | 11 | 13 | 15 | West Texas | Completed with minor quantity adjustments. | 8411 | 12 | 919 | 1915 | 906 | 6070 | 876 | good | 0.075 | 0.2 | 2 | complete
HIST-0172 | bunker_renovation | 266 | 70185.45 | 9 | 7 | 8 | West Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 8196 | 3461 | 275 | good | 0.05 | 0.18 | 1 | complete
HIST-0173 | fairway_grassing | 208130 | 153700.62 | 9 | 10 | 13 | East Texas | Scope change approved during construction. | 208130 | 8 | 0 | 0 | 0 | 29945 | 385 | moderate | 0.125 | 0.15 | 3 | complete
HIST-0174 | fairway_grassing | 61143 | 126886.99 | 16 | 19 | 17 | Oklahoma | Scope change approved during construction. | 61143 | 12 | 0 | 0 | 0 | 45628 | 547 | good | 0.125 | 0.2 | 0 | complete
HIST-0175 | new_putting_green | 13785 | 173048.75 | 13 | 28 | 28 | North Texas | Utility coordination added schedule risk. | 13785 | 6 | 1330 | 1755 | 788 | 18393 | 1225 | moderate | 0.05 | 0.2 | 0 | complete
HIST-0176 | fairway_grassing | 142349 | 69302.32 | 8 | 12 | 13 | Oklahoma | Additional hauling required due to site conditions. | 142349 | 6 | 0 | 0 | 0 | 37944 | 1392 | good | 0.15 | 0.12 | 1 | minor_scope_gap
HIST-0177 | putting_green_renovation | 8510 | 115009.86 | 8 | 23 | 22 | Oklahoma | Completed with standard site access. | 8510 | 12 | 916 | 1087 | 578 | 8826 | 250 | moderate | 0.15 | 0.2 | 0 | complete
HIST-0178 | fairway_grassing | 71704 | 76724.8 | 7 | 8 | 10 | Arkansas | Utility coordination added schedule risk. | 71704 | 10 | 0 | 0 | 0 | 61289 | 854 | good | 0.125 | 0.12 | 2 | complete
HIST-0179 | drainage_renovation | 1099 | 134932.36 | 11 | 22 | 22 | North Texas | Completed with standard site access. | 0 | 0 | 718 | 0 | 0 | 6250 | 417 | moderate | 0.075 | 0.2 | 0 | complete
HIST-0180 | putting_green_renovation | 12248 | 155121.67 | 12 | 15 | 21 | North Texas | Material delivery timing affected productivity. | 12248 | 12 | 869 | 1308 | 1238 | 18669 | 248 | good | 0.125 | 0.15 | 6 | complete
HIST-0181 | irrigation_renovation | 2635 | 57555.9 | 8 | 11 | 9 | North Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 2635 | 0 | 2188 | 743 | moderate | 0.125 | 0.1 | 0 | complete
HIST-0182 | tee_renovation | 20729 | 46602.73 | 6 | 10 | 11 | West Texas | Completed with standard site access. | 20729 | 12 | 397 | 762 | 0 | 19618 | 438 | moderate | 0.125 | 0.2 | 1 | complete
HIST-0183 | tee_renovation | 15078 | 72253.86 | 8 | 10 | 8 | North Texas | Completed with standard site access. | 15078 | 8 | 511 | 919 | 0 | 18151 | 207 | good | 0.075 | 0.12 | 0 | complete
HIST-0184 | irrigation_renovation | 3040 | 87428.72 | 12 | 10 | 14 | North Texas | Completed with standard site access. | 0 | 0 | 0 | 3040 | 0 | 4645 | 1400 | good | 0.075 | 0.1 | 4 | complete
HIST-0185 | irrigation_renovation | 7591 | 144432.77 | 8 | 12 | 13 | Arkansas | Minor weather delay; scope completed. | 0 | 0 | 0 | 7591 | 0 | 4363 | 1178 | moderate | 0.125 | 0.2 | 1 | complete
HIST-0186 | putting_green_renovation | 7945 | 148358.57 | 11 | 10 | 10 | Oklahoma | Additional hauling required due to site conditions. | 7945 | 10 | 496 | 1417 | 495 | 21600 | 344 | good | 0.125 | 0.1 | 0 | complete
HIST-0187 | drainage_renovation | 4861 | 97577.14 | 10 | 10 | 8 | Oklahoma | Completed with standard site access. | 0 | 0 | 4046 | 0 | 0 | 879 | 1316 | good | 0.1 | 0.15 | 0 | complete
HIST-0188 | tee_renovation | 24285 | 41483.06 | 8 | 6 | 3 | East Texas | Completed with minor quantity adjustments. | 24285 | 12 | 451 | 713 | 0 | 11558 | 466 | good | 0.125 | 0.15 | 0 | complete
HIST-0189 | tee_renovation | 12118 | 79515.31 | 7 | 14 | 16 | West Texas | Crew productivity was near plan. | 12118 | 8 | 398 | 917 | 0 | 12361 | 192 | good | 0.125 | 0.2 | 2 | complete
HIST-0190 | fairway_grassing | 110712 | 102421.91 | 16 | 16 | 15 | Central Texas | Material delivery timing affected productivity. | 110712 | 12 | 0 | 0 | 0 | 45920 | 1768 | good | 0.15 | 0.1 | 0 | complete
HIST-0191 | putting_green_renovation | 12881 | 104127.17 | 7 | 16 | 17 | East Texas | Scope change approved during construction. | 12881 | 8 | 505 | 1015 | 1465 | 15342 | 488 | good | 0.15 | 0.1 | 1 | complete
HIST-0192 | tee_renovation | 11974 | 64314.72 | 9 | 7 | 5 | Oklahoma | Minor weather delay; scope completed. | 11974 | 12 | 234 | 502 | 0 | 20816 | 161 | constrained | 0.125 | 0.2 | 0 | complete
HIST-0193 | tee_renovation | 24343 | 85767.32 | 7 | 13 | 15 | Oklahoma | Minor weather delay; scope completed. | 24343 | 12 | 411 | 908 | 0 | 25091 | 443 | constrained | 0.15 | 0.12 | 0 | complete
HIST-0194 | new_putting_green | 9036 | 168757.35 | 8 | 34 | 38 | East Texas | Scope change approved during construction. | 9036 | 12 | 1347 | 1842 | 493 | 22044 | 848 | constrained | 0.075 | 0.2 | 2 | minor_scope_gap
HIST-0195 | fairway_grassing | 62286 | 145207.85 | 13 | 13 | 14 | Arkansas | Final quantities reconciled against field measurements. | 62286 | 6 | 0 | 0 | 0 | 30912 | 1580 | moderate | 0.05 | 0.12 | 1 | complete
HIST-0196 | drainage_renovation | 3763 | 92496.29 | 12 | 21 | 22 | Arkansas | Scope change approved during construction. | 0 | 0 | 2549 | 0 | 0 | 5394 | 1459 | moderate | 0.125 | 0.12 | 1 | complete
HIST-0197 | bunker_renovation | 328 | 75668.23 | 7 | 9 | 10 | Central Texas | Crew productivity was near plan. | 0 | 0 | 0 | 0 | 2806 | 2256 | 244 | good | 0.1 | 0.15 | 1 | complete
HIST-0198 | irrigation_renovation | 6003 | 134019.77 | 7 | 10 | 10 | North Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 6003 | 0 | 2813 | 1182 | good | 0.1 | 0.12 | 0 | complete
HIST-0199 | new_putting_green | 9724 | 232775.93 | 15 | 32 | 34 | North Texas | Crew productivity was near plan. | 9724 | 12 | 869 | 2059 | 572 | 11653 | 839 | moderate | 0.1 | 0.2 | 2 | complete
HIST-0200 | tee_renovation | 13585 | 46611.31 | 6 | 11 | 11 | East Texas | Crew productivity was near plan. | 13585 | 12 | 148 | 357 | 0 | 9401 | 338 | moderate | 0.125 | 0.12 | 0 | complete
HIST-0201 | tee_renovation | 17548 | 65987.68 | 9 | 13 | 16 | Central Texas | Scope change approved during construction. | 17548 | 12 | 170 | 345 | 0 | 9606 | 268 | good | 0.15 | 0.15 | 3 | complete
HIST-0202 | putting_green_renovation | 13961 | 146083.69 | 8 | 16 | 21 | Arkansas | Additional hauling required due to site conditions. | 13961 | 6 | 772 | 1626 | 819 | 14817 | 881 | constrained | 0.1 | 0.2 | 3 | complete
HIST-0203 | fairway_grassing | 184776 | 134904.76 | 12 | 8 | 8 | West Texas | Utility coordination added schedule risk. | 184776 | 12 | 0 | 0 | 0 | 57030 | 1502 | moderate | 0.15 | 0.12 | 0 | complete
HIST-0204 | irrigation_renovation | 4406 | 74907.45 | 6 | 17 | 18 | West Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 4406 | 0 | 5325 | 441 | good | 0.15 | 0.2 | 1 | minor_scope_gap
HIST-0205 | new_putting_green | 11388 | 224794.57 | 10 | 33 | 31 | West Texas | Minor weather delay; scope completed. | 11388 | 12 | 988 | 1438 | 205 | 10130 | 491 | moderate | 0.1 | 0.18 | 0 | complete
HIST-0206 | putting_green_renovation | 7682 | 118885.55 | 11 | 10 | 11 | East Texas | Completed with minor quantity adjustments. | 7682 | 10 | 311 | 704 | 166 | 7523 | 294 | constrained | 0.125 | 0.2 | 0 | complete
HIST-0207 | new_putting_green | 13890 | 161750.3 | 13 | 23 | 22 | West Texas | Completed with minor quantity adjustments. | 13890 | 12 | 2125 | 2528 | 463 | 10785 | 369 | moderate | 0.125 | 0.15 | 0 | complete
HIST-0208 | new_putting_green | 7852 | 231199.99 | 10 | 27 | 30 | Oklahoma | Completed with minor quantity adjustments. | 7852 | 12 | 1097 | 1426 | 1 | 14976 | 1198 | moderate | 0.075 | 0.18 | 3 | complete
HIST-0209 | tee_renovation | 9839 | 78869.88 | 8 | 11 | 14 | West Texas | Utility coordination added schedule risk. | 9839 | 12 | 299 | 434 | 0 | 19692 | 202 | constrained | 0.15 | 0.15 | 1 | complete
HIST-0210 | irrigation_renovation | 6912 | 86303.36 | 10 | 12 | 10 | Arkansas | Material delivery timing affected productivity. | 0 | 0 | 0 | 6912 | 0 | 7462 | 1264 | moderate | 0.075 | 0.1 | 0 | complete
HIST-0211 | new_putting_green | 15611 | 226545.49 | 11 | 31 | 30 | West Texas | Scope change approved during construction. | 15611 | 10 | 1317 | 1640 | 1123 | 12589 | 472 | good | 0.1 | 0.12 | 0 | complete
HIST-0212 | drainage_renovation | 3507 | 110999.62 | 10 | 13 | 15 | West Texas | Additional hauling required due to site conditions. | 0 | 0 | 2831 | 0 | 0 | 1329 | 376 | moderate | 0.05 | 0.18 | 2 | complete
HIST-0213 | irrigation_renovation | 10331 | 138667.81 | 10 | 26 | 27 | West Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 10331 | 0 | 2709 | 1069 | good | 0.05 | 0.18 | 1 | complete
HIST-0214 | putting_green_renovation | 13161 | 123488.05 | 8 | 20 | 20 | East Texas | Additional hauling required due to site conditions. | 13161 | 12 | 787 | 1518 | 131 | 13753 | 254 | good | 0.075 | 0.1 | 0 | complete
HIST-0215 | new_putting_green | 11661 | 194187.1 | 11 | 27 | 32 | Arkansas | Unexpected subsurface conditions increased effort. | 11661 | 12 | 814 | 1843 | 2266 | 19376 | 788 | constrained | 0.1 | 0.18 | 3 | complete
HIST-0216 | irrigation_renovation | 9247 | 94751.94 | 9 | 25 | 29 | Arkansas | Completed with standard site access. | 0 | 0 | 0 | 9247 | 0 | 2493 | 858 | good | 0.05 | 0.2 | 4 | complete
HIST-0217 | putting_green_renovation | 7582 | 106382.23 | 6 | 12 | 11 | North Texas | Utility coordination added schedule risk. | 7582 | 10 | 410 | 1014 | 1211 | 6781 | 424 | good | 0.1 | 0.2 | 0 | complete
HIST-0218 | putting_green_renovation | 6567 | 169658.91 | 10 | 22 | 22 | Central Texas | Final quantities reconciled against field measurements. | 6567 | 10 | 1114 | 1619 | 1010 | 8558 | 309 | moderate | 0.15 | 0.12 | 0 | complete
HIST-0219 | tee_renovation | 17082 | 45515.47 | 5 | 10 | 16 | North Texas | Material delivery timing affected productivity. | 17082 | 12 | 271 | 497 | 0 | 20193 | 477 | moderate | 0.1 | 0.15 | 6 | complete
HIST-0220 | fairway_grassing | 78588 | 95422.19 | 9 | 25 | 26 | Oklahoma | Completed with minor quantity adjustments. | 78588 | 12 | 0 | 0 | 0 | 25998 | 1272 | moderate | 0.15 | 0.15 | 1 | complete
HIST-0221 | irrigation_renovation | 6922 | 124640.76 | 9 | 21 | 21 | North Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 6922 | 0 | 6702 | 1265 | moderate | 0.1 | 0.12 | 0 | complete
HIST-0222 | irrigation_renovation | 6352 | 62459.22 | 9 | 24 | 27 | Oklahoma | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 6352 | 0 | 1649 | 1308 | good | 0.15 | 0.18 | 3 | complete
HIST-0223 | drainage_renovation | 5722 | 134526.11 | 12 | 11 | 12 | Oklahoma | Additional hauling required due to site conditions. | 0 | 0 | 4041 | 0 | 0 | 3449 | 1590 | constrained | 0.05 | 0.2 | 0 | complete
HIST-0224 | bunker_renovation | 504 | 47529.48 | 9 | 15 | 21 | West Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 8843 | 5658 | 272 | good | 0.15 | 0.18 | 6 | complete
HIST-0225 | putting_green_renovation | 9416 | 122256.8 | 12 | 16 | 17 | Central Texas | Completed with minor quantity adjustments. | 9416 | 12 | 955 | 1157 | 1383 | 11779 | 270 | good | 0.125 | 0.18 | 1 | complete
HIST-0226 | irrigation_renovation | 9325 | 106785.47 | 13 | 27 | 30 | West Texas | Minor weather delay; scope completed. | 0 | 0 | 0 | 9325 | 0 | 3792 | 1433 | good | 0.075 | 0.12 | 3 | complete
HIST-0227 | irrigation_renovation | 8040 | 116153.16 | 7 | 11 | 13 | East Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 8040 | 0 | 5353 | 1101 | moderate | 0.075 | 0.12 | 2 | complete
HIST-0228 | putting_green_renovation | 13340 | 157771.88 | 12 | 18 | 19 | Arkansas | Utility coordination added schedule risk. | 13340 | 12 | 561 | 1324 | 342 | 12146 | 321 | constrained | 0.15 | 0.2 | 0 | complete
HIST-0229 | irrigation_renovation | 3996 | 137135.52 | 11 | 12 | 13 | Oklahoma | Completed with standard site access. | 0 | 0 | 0 | 3996 | 0 | 5349 | 408 | good | 0.1 | 0.2 | 1 | complete
HIST-0230 | putting_green_renovation | 12833 | 85429.09 | 11 | 10 | 10 | Arkansas | Crew productivity was near plan. | 12833 | 12 | 1295 | 1526 | 1665 | 20662 | 796 | moderate | 0.05 | 0.12 | 0 | complete
HIST-0231 | new_putting_green | 11358 | 192727.1 | 12 | 25 | 25 | Arkansas | Utility coordination added schedule risk. | 11358 | 12 | 1348 | 2088 | 2165 | 18508 | 730 | good | 0.15 | 0.2 | 0 | complete
HIST-0232 | drainage_renovation | 6463 | 70386.79 | 6 | 15 | 16 | Oklahoma | Additional hauling required due to site conditions. | 0 | 0 | 3636 | 0 | 0 | 3355 | 380 | good | 0.05 | 0.18 | 1 | complete
HIST-0233 | fairway_grassing | 46495 | 128218.55 | 11 | 16 | 15 | East Texas | Unexpected subsurface conditions increased effort. | 46495 | 6 | 0 | 0 | 0 | 35161 | 756 | moderate | 0.15 | 0.12 | 0 | complete
HIST-0234 | fairway_grassing | 159716 | 68349.94 | 8 | 19 | 17 | North Texas | Unexpected subsurface conditions increased effort. | 159716 | 12 | 0 | 0 | 0 | 59282 | 1551 | good | 0.1 | 0.2 | 0 | complete
HIST-0235 | bunker_renovation | 467 | 70391.22 | 8 | 8 | 5 | Oklahoma | Material delivery timing affected productivity. | 0 | 0 | 0 | 0 | 5188 | 1252 | 268 | good | 0.15 | 0.1 | 0 | complete
HIST-0236 | fairway_grassing | 186588 | 83826.74 | 10 | 15 | 14 | West Texas | Utility coordination added schedule risk. | 186588 | 6 | 0 | 0 | 0 | 21627 | 1254 | constrained | 0.05 | 0.15 | 0 | complete
HIST-0237 | tee_renovation | 22621 | 67547.21 | 9 | 15 | 16 | Arkansas | Additional hauling required due to site conditions. | 22621 | 12 | 425 | 877 | 0 | 13936 | 262 | good | 0.125 | 0.18 | 1 | complete
HIST-0238 | bunker_renovation | 1144 | 82989.86 | 6 | 15 | 16 | Arkansas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 8655 | 5050 | 307 | moderate | 0.125 | 0.12 | 1 | complete
HIST-0239 | tee_renovation | 13918 | 83507.99 | 9 | 11 | 11 | Arkansas | Crew productivity was near plan. | 13918 | 8 | 514 | 704 | 0 | 25367 | 505 | moderate | 0.125 | 0.2 | 0 | complete
HIST-0240 | drainage_renovation | 934 | 55733.83 | 7 | 18 | 20 | Arkansas | Completed with standard site access. | 0 | 0 | 378 | 0 | 0 | 8752 | 852 | constrained | 0.075 | 0.1 | 0 | complete
HIST-0241 | putting_green_renovation | 10229 | 144602.35 | 11 | 20 | 20 | North Texas | Additional hauling required due to site conditions. | 10229 | 12 | 709 | 1886 | 411 | 6109 | 484 | good | 0.05 | 0.2 | 0 | complete
HIST-0242 | fairway_grassing | 171595 | 86390.89 | 11 | 15 | 15 | Central Texas | Completed with minor quantity adjustments. | 171595 | 10 | 0 | 0 | 0 | 16732 | 1072 | good | 0.05 | 0.15 | 0 | complete
HIST-0243 | bunker_renovation | 1116 | 59702.49 | 9 | 14 | 14 | Arkansas | Minor weather delay; scope completed. | 0 | 0 | 0 | 0 | 8546 | 1358 | 373 | good | 0.1 | 0.1 | 0 | complete
HIST-0244 | putting_green_renovation | 12199 | 179194.9 | 9 | 17 | 19 | East Texas | Crew productivity was near plan. | 12199 | 12 | 506 | 1437 | 1512 | 12921 | 458 | constrained | 0.05 | 0.2 | 0 | complete
HIST-0245 | tee_renovation | 22023 | 89321.81 | 9 | 7 | 8 | East Texas | Unexpected subsurface conditions increased effort. | 22023 | 12 | 567 | 717 | 0 | 15806 | 350 | moderate | 0.125 | 0.2 | 1 | complete
HIST-0246 | bunker_renovation | 1224 | 60777.86 | 8 | 16 | 16 | West Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 8794 | 5448 | 156 | moderate | 0.15 | 0.15 | 0 | complete
HIST-0247 | fairway_grassing | 205244 | 131521.44 | 9 | 12 | 12 | West Texas | Utility coordination added schedule risk. | 205244 | 12 | 0 | 0 | 0 | 25860 | 1558 | moderate | 0.05 | 0.15 | 0 | complete
HIST-0248 | irrigation_renovation | 1818 | 103087.27 | 7 | 13 | 16 | North Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 1818 | 0 | 3301 | 479 | good | 0.075 | 0.12 | 3 | complete
HIST-0249 | putting_green_renovation | 13910 | 96334.29 | 6 | 21 | 21 | North Texas | Unexpected subsurface conditions increased effort. | 13910 | 10 | 470 | 1134 | 139 | 8738 | 446 | constrained | 0.05 | 0.18 | 0 | complete
HIST-0250 | tee_renovation | 19566 | 50581.81 | 6 | 15 | 13 | Central Texas | Minor weather delay; scope completed. | 19566 | 10 | 570 | 877 | 0 | 13101 | 149 | good | 0.05 | 0.12 | 0 | complete
HIST-0251 | tee_renovation | 15899 | 85059.25 | 6 | 6 | 6 | Oklahoma | Completed with standard site access. | 15899 | 6 | 362 | 432 | 0 | 12865 | 527 | moderate | 0.125 | 0.18 | 0 | complete
HIST-0252 | tee_renovation | 13752 | 95444.17 | 5 | 11 | 12 | Arkansas | Completed with standard site access. | 13752 | 6 | 330 | 558 | 0 | 19790 | 274 | constrained | 0.05 | 0.1 | 0 | complete
HIST-0253 | fairway_grassing | 117021 | 124952.29 | 16 | 18 | 20 | West Texas | Minor weather delay; scope completed. | 117021 | 8 | 0 | 0 | 0 | 32727 | 834 | moderate | 0.15 | 0.2 | 2 | complete
HIST-0254 | fairway_grassing | 153684 | 138824.86 | 10 | 8 | 6 | West Texas | Material delivery timing affected productivity. | 153684 | 12 | 0 | 0 | 0 | 56865 | 1018 | moderate | 0.15 | 0.2 | 0 | complete
HIST-0255 | new_putting_green | 7137 | 140882.97 | 12 | 27 | 28 | Oklahoma | Utility coordination added schedule risk. | 7137 | 12 | 586 | 1255 | 2499 | 25731 | 740 | good | 0.125 | 0.1 | 1 | complete
HIST-0256 | fairway_grassing | 181871 | 120858.82 | 12 | 12 | 12 | North Texas | Minor weather delay; scope completed. | 181871 | 12 | 0 | 0 | 0 | 27581 | 596 | moderate | 0.075 | 0.18 | 0 | complete
HIST-0257 | fairway_grassing | 77685 | 88902.17 | 14 | 8 | 9 | Oklahoma | Scope change approved during construction. | 77685 | 12 | 0 | 0 | 0 | 39956 | 1054 | good | 0.15 | 0.18 | 1 | complete
HIST-0258 | tee_renovation | 24502 | 68440.78 | 6 | 11 | 11 | Central Texas | Completed with standard site access. | 24502 | 12 | 106 | 281 | 0 | 13064 | 307 | good | 0.15 | 0.15 | 0 | complete
HIST-0259 | drainage_renovation | 4128 | 84871.89 | 9 | 9 | 12 | North Texas | Utility coordination added schedule risk. | 0 | 0 | 3485 | 0 | 0 | 4074 | 406 | moderate | 0.15 | 0.15 | 3 | complete
HIST-0260 | drainage_renovation | 1839 | 141678.53 | 11 | 13 | 17 | Arkansas | Completed with standard site access. | 0 | 0 | 711 | 0 | 0 | 6839 | 759 | constrained | 0.05 | 0.15 | 2 | complete
HIST-0261 | new_putting_green | 11603 | 200526.22 | 14 | 25 | 27 | Central Texas | Crew productivity was near plan. | 11603 | 12 | 766 | 1533 | 2935 | 17974 | 1276 | good | 0.15 | 0.1 | 2 | complete
HIST-0262 | tee_renovation | 25335 | 73576.04 | 7 | 12 | 13 | Arkansas | Minor weather delay; scope completed. | 25335 | 10 | 279 | 347 | 0 | 17409 | 364 | moderate | 0.15 | 0.18 | 1 | complete
HIST-0263 | bunker_renovation | 1174 | 98923.35 | 7 | 12 | 12 | Arkansas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 9889 | 3329 | 497 | good | 0.125 | 0.2 | 0 | complete
HIST-0264 | putting_green_renovation | 9426 | 154366.75 | 10 | 21 | 22 | Central Texas | Material delivery timing affected productivity. | 9426 | 8 | 503 | 762 | 576 | 20990 | 710 | moderate | 0.1 | 0.15 | 1 | complete
HIST-0265 | bunker_renovation | 796 | 52193.5 | 9 | 8 | 8 | Central Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 9099 | 2991 | 442 | moderate | 0.075 | 0.12 | 0 | complete
HIST-0266 | putting_green_renovation | 13431 | 170319.82 | 12 | 23 | 25 | West Texas | Utility coordination added schedule risk. | 13431 | 10 | 680 | 1318 | 1531 | 19645 | 568 | moderate | 0.075 | 0.2 | 2 | complete
HIST-0267 | putting_green_renovation | 9999 | 131976.27 | 11 | 20 | 22 | Arkansas | Material delivery timing affected productivity. | 9999 | 10 | 1027 | 1369 | 1110 | 8149 | 817 | good | 0.15 | 0.15 | 2 | complete
HIST-0268 | irrigation_renovation | 8313 | 80227.34 | 12 | 15 | 15 | Oklahoma | Completed with standard site access. | 0 | 0 | 0 | 8313 | 0 | 3440 | 1275 | good | 0.075 | 0.12 | 0 | complete
HIST-0269 | tee_renovation | 8736 | 51587.47 | 9 | 15 | 16 | Oklahoma | Final quantities reconciled against field measurements. | 8736 | 8 | 443 | 768 | 0 | 20991 | 458 | good | 0.125 | 0.1 | 1 | complete
HIST-0270 | putting_green_renovation | 5980 | 105707.32 | 7 | 13 | 16 | Oklahoma | Completed with standard site access. | 5980 | 12 | 1091 | 1538 | 1647 | 18816 | 322 | moderate | 0.1 | 0.1 | 3 | complete
HIST-0271 | irrigation_renovation | 5171 | 105636.44 | 7 | 25 | 23 | Central Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 5171 | 0 | 2446 | 453 | good | 0.125 | 0.1 | 0 | complete
HIST-0272 | drainage_renovation | 3464 | 55148.83 | 12 | 18 | 18 | Arkansas | Completed with minor quantity adjustments. | 0 | 0 | 1802 | 0 | 0 | 1898 | 1367 | good | 0.15 | 0.2 | 0 | complete
HIST-0273 | putting_green_renovation | 13050 | 139238.61 | 7 | 22 | 20 | East Texas | Completed with standard site access. | 13050 | 12 | 613 | 881 | 1349 | 11273 | 277 | moderate | 0.15 | 0.18 | 0 | complete
HIST-0274 | tee_renovation | 19113 | 46218.15 | 4 | 8 | 9 | North Texas | Material delivery timing affected productivity. | 19113 | 10 | 327 | 490 | 0 | 8116 | 256 | constrained | 0.05 | 0.2 | 0 | complete
HIST-0275 | fairway_grassing | 145448 | 105389.35 | 16 | 10 | 10 | Arkansas | Final quantities reconciled against field measurements. | 145448 | 10 | 0 | 0 | 0 | 44839 | 596 | good | 0.075 | 0.15 | 0 | complete
HIST-0276 | fairway_grassing | 77300 | 134905.41 | 11 | 22 | 20 | Oklahoma | Additional hauling required due to site conditions. | 77300 | 12 | 0 | 0 | 0 | 36997 | 1384 | moderate | 0.05 | 0.12 | 0 | complete
HIST-0277 | tee_renovation | 18847 | 45865.01 | 6 | 13 | 11 | North Texas | Material delivery timing affected productivity. | 18847 | 12 | 145 | 282 | 0 | 13964 | 288 | good | 0.1 | 0.15 | 0 | complete
HIST-0278 | new_putting_green | 14093 | 145507.01 | 14 | 22 | 22 | Central Texas | Minor weather delay; scope completed. | 14093 | 12 | 760 | 1006 | 2912 | 11118 | 811 | moderate | 0.075 | 0.12 | 0 | complete
HIST-0279 | irrigation_renovation | 3715 | 74862.32 | 8 | 15 | 15 | West Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 3715 | 0 | 4897 | 1396 | moderate | 0.1 | 0.15 | 0 | complete
HIST-0280 | irrigation_renovation | 2578 | 83700.18 | 9 | 18 | 21 | North Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 2578 | 0 | 4137 | 849 | moderate | 0.05 | 0.2 | 3 | complete
HIST-0281 | bunker_renovation | 621 | 78446.98 | 9 | 15 | 16 | East Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 4992 | 1482 | 606 | good | 0.075 | 0.18 | 1 | complete
HIST-0282 | irrigation_renovation | 7670 | 123647.68 | 8 | 21 | 22 | East Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 7670 | 0 | 6400 | 590 | constrained | 0.125 | 0.18 | 0 | complete
HIST-0283 | bunker_renovation | 432 | 106674.2 | 10 | 8 | 7 | Central Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 0 | 6400 | 907 | 296 | good | 0.125 | 0.2 | 0 | complete
HIST-0284 | fairway_grassing | 79943 | 97529.95 | 10 | 15 | 15 | West Texas | Additional hauling required due to site conditions. | 79943 | 12 | 0 | 0 | 0 | 64625 | 1515 | moderate | 0.125 | 0.1 | 0 | complete
HIST-0285 | drainage_renovation | 4505 | 83775.99 | 8 | 13 | 14 | East Texas | Minor weather delay; scope completed. | 0 | 0 | 3000 | 0 | 0 | 5767 | 571 | good | 0.125 | 0.15 | 1 | complete
HIST-0286 | drainage_renovation | 5644 | 55446.13 | 10 | 10 | 13 | West Texas | Crew productivity was near plan. | 0 | 0 | 4608 | 0 | 0 | 4269 | 881 | moderate | 0.125 | 0.2 | 3 | complete
HIST-0287 | tee_renovation | 13072 | 75290.35 | 7 | 15 | 11 | Central Texas | Minor weather delay; scope completed. | 13072 | 6 | 499 | 836 | 0 | 9889 | 303 | good | 0.075 | 0.1 | 0 | complete
HIST-0288 | tee_renovation | 23919 | 49139.63 | 7 | 8 | 7 | Central Texas | Completed with minor quantity adjustments. | 23919 | 12 | 294 | 375 | 0 | 22762 | 247 | moderate | 0.15 | 0.2 | 0 | complete
HIST-0289 | putting_green_renovation | 6326 | 95035.25 | 10 | 11 | 8 | North Texas | Completed with minor quantity adjustments. | 6326 | 8 | 927 | 1915 | 920 | 18281 | 383 | good | 0.075 | 0.12 | 0 | complete
HIST-0290 | tee_renovation | 16781 | 56175.53 | 5 | 6 | 6 | Oklahoma | Unexpected subsurface conditions increased effort. | 16781 | 12 | 104 | 255 | 0 | 8407 | 501 | good | 0.075 | 0.12 | 0 | complete
HIST-0291 | new_putting_green | 15737 | 224580.01 | 14 | 27 | 26 | West Texas | Completed with standard site access. | 15737 | 12 | 841 | 1453 | 1185 | 19474 | 465 | good | 0.15 | 0.12 | 0 | complete
HIST-0292 | putting_green_renovation | 6008 | 152635.78 | 6 | 22 | 23 | Arkansas | Completed with minor quantity adjustments. | 6008 | 6 | 1266 | 1544 | 828 | 8437 | 790 | constrained | 0.125 | 0.15 | 0 | complete
HIST-0293 | putting_green_renovation | 7734 | 130755.3 | 9 | 21 | 22 | Oklahoma | Completed with standard site access. | 7734 | 8 | 672 | 1443 | 301 | 19861 | 496 | moderate | 0.075 | 0.18 | 1 | minor_scope_gap
HIST-0294 | tee_renovation | 12254 | 42255.44 | 6 | 11 | 13 | East Texas | Final quantities reconciled against field measurements. | 12254 | 10 | 137 | 165 | 0 | 23260 | 426 | good | 0.125 | 0.12 | 2 | complete
HIST-0295 | bunker_renovation | 1003 | 88593.99 | 7 | 11 | 17 | Central Texas | Completed with standard site access. | 0 | 0 | 0 | 0 | 2869 | 3508 | 537 | moderate | 0.125 | 0.1 | 6 | complete
HIST-0296 | irrigation_renovation | 7152 | 71857.94 | 12 | 22 | 28 | Oklahoma | Additional hauling required due to site conditions. | 0 | 0 | 0 | 7152 | 0 | 1549 | 328 | good | 0.125 | 0.12 | 6 | complete
HIST-0297 | putting_green_renovation | 8207 | 94788.93 | 6 | 17 | 19 | Arkansas | Crew productivity was near plan. | 8207 | 12 | 585 | 1062 | 1363 | 5107 | 816 | moderate | 0.075 | 0.12 | 2 | complete
HIST-0298 | putting_green_renovation | 10275 | 185541.28 | 8 | 15 | 14 | Oklahoma | Crew productivity was near plan. | 10275 | 6 | 1186 | 1517 | 236 | 6062 | 630 | constrained | 0.05 | 0.15 | 0 | complete
HIST-0299 | tee_renovation | 16592 | 53008.65 | 8 | 6 | 9 | East Texas | Minor weather delay; scope completed. | 16592 | 12 | 91 | 211 | 0 | 16801 | 404 | moderate | 0.15 | 0.15 | 3 | complete
HIST-0300 | bunker_renovation | 1089 | 57987.42 | 8 | 8 | 9 | Central Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 3557 | 1519 | 431 | moderate | 0.075 | 0.15 | 1 | complete
HIST-0301 | tee_renovation | 17837 | 48573.63 | 6 | 6 | 10 | Oklahoma | Completed with minor quantity adjustments. | 17837 | 8 | 375 | 613 | 0 | 22634 | 480 | constrained | 0.05 | 0.1 | 2 | complete
HIST-0302 | bunker_renovation | 869 | 109937.56 | 7 | 12 | 15 | East Texas | Completed with standard site access. | 0 | 0 | 0 | 0 | 9458 | 5599 | 266 | moderate | 0.075 | 0.2 | 3 | complete
HIST-0303 | fairway_grassing | 90266 | 134739.05 | 11 | 22 | 22 | Arkansas | Minor weather delay; scope completed. | 90266 | 12 | 0 | 0 | 0 | 55506 | 1365 | good | 0.1 | 0.2 | 0 | complete
HIST-0304 | tee_renovation | 7156 | 86714.02 | 9 | 12 | 12 | Arkansas | Completed with minor quantity adjustments. | 7156 | 12 | 251 | 356 | 0 | 27374 | 310 | moderate | 0.05 | 0.1 | 0 | complete
HIST-0305 | bunker_renovation | 252 | 114979.45 | 9 | 14 | 14 | West Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 0 | 8861 | 4893 | 439 | moderate | 0.15 | 0.18 | 0 | complete
HIST-0306 | bunker_renovation | 813 | 50657.59 | 10 | 15 | 17 | East Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 0 | 9947 | 1923 | 629 | moderate | 0.075 | 0.1 | 2 | complete
HIST-0307 | fairway_grassing | 141594 | 138100.9 | 11 | 24 | 25 | Oklahoma | Unexpected subsurface conditions increased effort. | 141594 | 12 | 0 | 0 | 0 | 46054 | 1774 | good | 0.125 | 0.15 | 1 | complete
HIST-0308 | drainage_renovation | 5673 | 118421.22 | 11 | 17 | 17 | North Texas | Crew productivity was near plan. | 0 | 0 | 4015 | 0 | 0 | 5364 | 1223 | moderate | 0.075 | 0.2 | 0 | complete
HIST-0309 | drainage_renovation | 6137 | 111002.2 | 5 | 12 | 11 | East Texas | Utility coordination added schedule risk. | 0 | 0 | 3259 | 0 | 0 | 6775 | 422 | moderate | 0.075 | 0.12 | 0 | complete
HIST-0310 | new_putting_green | 15755 | 179375.52 | 13 | 24 | 23 | West Texas | Minor weather delay; scope completed. | 15755 | 12 | 875 | 2192 | 3453 | 24928 | 732 | moderate | 0.1 | 0.2 | 0 | complete
HIST-0311 | tee_renovation | 10389 | 56651.53 | 4 | 6 | 5 | West Texas | Crew productivity was near plan. | 10389 | 12 | 224 | 312 | 0 | 16923 | 205 | moderate | 0.15 | 0.15 | 0 | complete
HIST-0312 | new_putting_green | 7621 | 203987.06 | 14 | 20 | 20 | East Texas | Additional hauling required due to site conditions. | 7621 | 12 | 647 | 1206 | 1920 | 25219 | 1049 | good | 0.125 | 0.1 | 0 | complete
HIST-0313 | putting_green_renovation | 13503 | 97010.33 | 10 | 15 | 14 | Central Texas | Unexpected subsurface conditions increased effort. | 13503 | 6 | 1434 | 2023 | 1153 | 14686 | 318 | good | 0.15 | 0.15 | 0 | complete
HIST-0314 | fairway_grassing | 209624 | 74734.29 | 16 | 11 | 14 | East Texas | Unexpected subsurface conditions increased effort. | 209624 | 12 | 0 | 0 | 0 | 46513 | 1152 | constrained | 0.15 | 0.15 | 1 | minor_scope_gap
HIST-0315 | tee_renovation | 22942 | 67752.37 | 8 | 13 | 10 | Oklahoma | Additional hauling required due to site conditions. | 22942 | 8 | 383 | 759 | 0 | 18901 | 445 | good | 0.05 | 0.15 | 0 | complete
HIST-0316 | putting_green_renovation | 11260 | 158927.95 | 8 | 19 | 23 | North Texas | Unexpected subsurface conditions increased effort. | 11260 | 10 | 662 | 1018 | 339 | 11529 | 770 | moderate | 0.1 | 0.12 | 4 | complete
HIST-0317 | irrigation_renovation | 4114 | 61410.61 | 12 | 12 | 12 | East Texas | Crew productivity was near plan. | 0 | 0 | 0 | 4114 | 0 | 7041 | 465 | good | 0.125 | 0.15 | 0 | complete
HIST-0318 | drainage_renovation | 4671 | 81224.15 | 5 | 13 | 10 | North Texas | Utility coordination added schedule risk. | 0 | 0 | 2522 | 0 | 0 | 8362 | 736 | good | 0.15 | 0.12 | 0 | complete
HIST-0319 | irrigation_renovation | 6162 | 99953.21 | 9 | 22 | 25 | North Texas | Minor weather delay; scope completed. | 0 | 0 | 0 | 6162 | 0 | 809 | 471 | moderate | 0.1 | 0.2 | 3 | complete
HIST-0320 | putting_green_renovation | 7530 | 107235.41 | 8 | 23 | 20 | Central Texas | Utility coordination added schedule risk. | 7530 | 10 | 728 | 1170 | 1266 | 10567 | 887 | moderate | 0.075 | 0.18 | 0 | complete
HIST-0321 | irrigation_renovation | 4760 | 65439.38 | 6 | 19 | 18 | Central Texas | Scope change approved during construction. | 0 | 0 | 0 | 4760 | 0 | 5029 | 842 | moderate | 0.125 | 0.1 | 0 | complete
HIST-0322 | tee_renovation | 17315 | 38909.79 | 9 | 15 | 18 | East Texas | Material delivery timing affected productivity. | 17315 | 10 | 215 | 395 | 0 | 13953 | 307 | good | 0.05 | 0.18 | 3 | complete
HIST-0323 | irrigation_renovation | 2432 | 93875.79 | 10 | 24 | 27 | Arkansas | Scope change approved during construction. | 0 | 0 | 0 | 2432 | 0 | 5208 | 1722 | moderate | 0.075 | 0.18 | 3 | complete
HIST-0324 | tee_renovation | 19781 | 44716.92 | 7 | 8 | 8 | Central Texas | Scope change approved during construction. | 19781 | 12 | 147 | 182 | 0 | 12612 | 487 | good | 0.15 | 0.15 | 0 | complete
HIST-0325 | drainage_renovation | 974 | 91263.98 | 10 | 10 | 11 | Central Texas | Additional hauling required due to site conditions. | 0 | 0 | 431 | 0 | 0 | 1543 | 1531 | moderate | 0.05 | 0.15 | 1 | complete
HIST-0326 | fairway_grassing | 163067 | 86069.86 | 7 | 15 | 15 | West Texas | Completed with minor quantity adjustments. | 163067 | 12 | 0 | 0 | 0 | 30813 | 716 | moderate | 0.075 | 0.1 | 0 | complete
HIST-0327 | drainage_renovation | 5726 | 67092.31 | 11 | 15 | 17 | Oklahoma | Completed with minor quantity adjustments. | 0 | 0 | 4436 | 0 | 0 | 8722 | 1584 | constrained | 0.1 | 0.15 | 0 | complete
HIST-0328 | irrigation_renovation | 9348 | 139304.69 | 8 | 23 | 23 | West Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 9348 | 0 | 5683 | 841 | moderate | 0.15 | 0.12 | 0 | complete
HIST-0329 | new_putting_green | 15753 | 153869.13 | 14 | 21 | 22 | East Texas | Unexpected subsurface conditions increased effort. | 15753 | 12 | 2016 | 2513 | 3032 | 25622 | 1270 | good | 0.075 | 0.2 | 1 | complete
HIST-0330 | bunker_renovation | 662 | 82438.27 | 10 | 9 | 11 | West Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 8888 | 972 | 102 | moderate | 0.15 | 0.12 | 2 | complete
HIST-0331 | tee_renovation | 17767 | 55164.15 | 5 | 14 | 12 | East Texas | Completed with minor quantity adjustments. | 17767 | 12 | 414 | 918 | 0 | 20535 | 179 | moderate | 0.075 | 0.2 | 0 | complete
HIST-0332 | drainage_renovation | 4963 | 102404.38 | 7 | 15 | 16 | East Texas | Minor weather delay; scope completed. | 0 | 0 | 3885 | 0 | 0 | 877 | 1358 | good | 0.15 | 0.1 | 1 | complete
HIST-0333 | putting_green_renovation | 9631 | 92775.78 | 10 | 23 | 27 | Arkansas | Minor weather delay; scope completed. | 9631 | 12 | 1323 | 1648 | 1538 | 17984 | 697 | moderate | 0.1 | 0.2 | 4 | complete
HIST-0334 | bunker_renovation | 948 | 65642.19 | 8 | 7 | 10 | Oklahoma | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 10316 | 2316 | 395 | good | 0.05 | 0.1 | 3 | complete
HIST-0335 | new_putting_green | 7503 | 162902.52 | 14 | 34 | 34 | West Texas | Minor weather delay; scope completed. | 7503 | 12 | 959 | 2211 | 3224 | 25334 | 1163 | moderate | 0.05 | 0.1 | 0 | complete
HIST-0336 | tee_renovation | 22618 | 76438.12 | 8 | 9 | 12 | North Texas | Unexpected subsurface conditions increased effort. | 22618 | 8 | 343 | 806 | 0 | 12098 | 277 | constrained | 0.1 | 0.1 | 1 | complete
HIST-0337 | tee_renovation | 23138 | 77542.75 | 6 | 11 | 10 | Arkansas | Completed with standard site access. | 23138 | 12 | 173 | 373 | 0 | 11268 | 490 | good | 0.05 | 0.2 | 0 | complete
HIST-0338 | bunker_renovation | 255 | 73751.69 | 5 | 10 | 10 | Arkansas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 7567 | 1078 | 390 | good | 0.125 | 0.18 | 0 | complete
HIST-0339 | tee_renovation | 8850 | 58536.81 | 7 | 11 | 11 | North Texas | Final quantities reconciled against field measurements. | 8850 | 8 | 361 | 836 | 0 | 18208 | 187 | good | 0.125 | 0.1 | 0 | complete
HIST-0340 | putting_green_renovation | 8189 | 130387.52 | 12 | 22 | 24 | Oklahoma | Final quantities reconciled against field measurements. | 8189 | 12 | 461 | 684 | 1398 | 19286 | 734 | moderate | 0.075 | 0.12 | 2 | complete
HIST-0341 | drainage_renovation | 5655 | 71534.51 | 5 | 15 | 11 | East Texas | Material delivery timing affected productivity. | 0 | 0 | 2674 | 0 | 0 | 4671 | 1005 | moderate | 0.15 | 0.2 | 0 | complete
HIST-0342 | drainage_renovation | 4454 | 56811.66 | 12 | 12 | 13 | Arkansas | Unexpected subsurface conditions increased effort. | 0 | 0 | 2933 | 0 | 0 | 4337 | 1471 | moderate | 0.15 | 0.15 | 1 | complete
HIST-0343 | putting_green_renovation | 13887 | 114068.63 | 6 | 13 | 14 | Oklahoma | Additional hauling required due to site conditions. | 13887 | 12 | 566 | 702 | 1073 | 8799 | 518 | moderate | 0.05 | 0.15 | 1 | complete
HIST-0344 | irrigation_renovation | 5343 | 106814.35 | 9 | 11 | 14 | North Texas | Completed with standard site access. | 0 | 0 | 0 | 5343 | 0 | 5951 | 631 | moderate | 0.1 | 0.2 | 3 | complete
HIST-0345 | putting_green_renovation | 6748 | 92355.8 | 7 | 12 | 13 | East Texas | Minor weather delay; scope completed. | 6748 | 12 | 602 | 998 | 560 | 7667 | 231 | good | 0.125 | 0.18 | 1 | complete
HIST-0346 | bunker_renovation | 520 | 66077.8 | 9 | 8 | 8 | West Texas | Minor weather delay; scope completed. | 0 | 0 | 0 | 0 | 3646 | 4220 | 398 | moderate | 0.125 | 0.18 | 0 | complete
HIST-0347 | putting_green_renovation | 13648 | 162497.25 | 8 | 21 | 21 | Oklahoma | Unexpected subsurface conditions increased effort. | 13648 | 12 | 398 | 1053 | 1503 | 7259 | 270 | moderate | 0.125 | 0.2 | 0 | complete
HIST-0348 | tee_renovation | 21338 | 38319.49 | 6 | 13 | 13 | East Texas | Completed with minor quantity adjustments. | 21338 | 12 | 473 | 886 | 0 | 16816 | 341 | good | 0.15 | 0.1 | 0 | complete
HIST-0349 | irrigation_renovation | 9461 | 137623.93 | 9 | 27 | 27 | West Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 9461 | 0 | 4872 | 1790 | good | 0.1 | 0.15 | 0 | complete
HIST-0350 | drainage_renovation | 6287 | 68720.78 | 6 | 9 | 9 | Central Texas | Final quantities reconciled against field measurements. | 0 | 0 | 3967 | 0 | 0 | 620 | 643 | good | 0.125 | 0.1 | 0 | complete
HIST-0351 | fairway_grassing | 108058 | 158255.22 | 7 | 19 | 21 | East Texas | Utility coordination added schedule risk. | 108058 | 10 | 0 | 0 | 0 | 47908 | 448 | moderate | 0.15 | 0.15 | 2 | complete
HIST-0352 | bunker_renovation | 935 | 98881.22 | 5 | 10 | 6 | Oklahoma | Scope change approved during construction. | 0 | 0 | 0 | 0 | 8771 | 4476 | 646 | moderate | 0.125 | 0.1 | 0 | complete
HIST-0353 | bunker_renovation | 647 | 78785.18 | 7 | 12 | 10 | Oklahoma | Additional hauling required due to site conditions. | 0 | 0 | 0 | 0 | 6125 | 859 | 397 | good | 0.15 | 0.2 | 0 | complete
HIST-0354 | fairway_grassing | 147506 | 150334.33 | 11 | 10 | 16 | Central Texas | Additional hauling required due to site conditions. | 147506 | 12 | 0 | 0 | 0 | 58903 | 1102 | good | 0.1 | 0.18 | 6 | complete
HIST-0355 | irrigation_renovation | 9382 | 108892.76 | 8 | 21 | 20 | East Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 9382 | 0 | 5651 | 585 | moderate | 0.125 | 0.1 | 0 | complete
HIST-0356 | irrigation_renovation | 7570 | 63126.69 | 10 | 22 | 22 | North Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 7570 | 0 | 4244 | 552 | good | 0.125 | 0.12 | 0 | complete
HIST-0357 | tee_renovation | 18993 | 48939.66 | 4 | 13 | 16 | North Texas | Utility coordination added schedule risk. | 18993 | 12 | 310 | 651 | 0 | 12003 | 514 | good | 0.05 | 0.12 | 3 | complete
HIST-0358 | putting_green_renovation | 13115 | 125556.53 | 12 | 23 | 26 | West Texas | Final quantities reconciled against field measurements. | 13115 | 12 | 1643 | 1944 | 224 | 20628 | 628 | good | 0.075 | 0.18 | 3 | complete
HIST-0359 | putting_green_renovation | 5744 | 126305.68 | 10 | 10 | 9 | Oklahoma | Additional hauling required due to site conditions. | 5744 | 10 | 503 | 678 | 16 | 6866 | 818 | moderate | 0.075 | 0.2 | 0 | complete
HIST-0360 | tee_renovation | 15976 | 89244.7 | 6 | 7 | 11 | Central Texas | Unexpected subsurface conditions increased effort. | 15976 | 10 | 165 | 253 | 0 | 22428 | 352 | moderate | 0.125 | 0.2 | 4 | complete
HIST-0361 | irrigation_renovation | 4827 | 105103.08 | 9 | 14 | 22 | North Texas | Minor weather delay; scope completed. | 0 | 0 | 0 | 4827 | 0 | 7803 | 743 | constrained | 0.1 | 0.15 | 6 | complete
HIST-0362 | putting_green_renovation | 6860 | 146584.23 | 10 | 21 | 21 | Arkansas | Completed with standard site access. | 6860 | 8 | 890 | 1248 | 1036 | 12040 | 579 | good | 0.075 | 0.12 | 0 | complete
HIST-0363 | bunker_renovation | 485 | 85471.8 | 7 | 11 | 10 | Arkansas | Completed with standard site access. | 0 | 0 | 0 | 0 | 7391 | 5620 | 615 | good | 0.1 | 0.12 | 0 | complete
HIST-0364 | tee_renovation | 16427 | 89115.99 | 5 | 13 | 13 | Arkansas | Unexpected subsurface conditions increased effort. | 16427 | 12 | 410 | 832 | 0 | 17662 | 300 | constrained | 0.05 | 0.18 | 0 | complete
HIST-0365 | tee_renovation | 19431 | 78971.04 | 4 | 14 | 15 | Central Texas | Completed with standard site access. | 19431 | 12 | 467 | 854 | 0 | 10525 | 454 | constrained | 0.1 | 0.15 | 0 | complete
HIST-0366 | new_putting_green | 15089 | 231391.8 | 10 | 19 | 23 | North Texas | Utility coordination added schedule risk. | 15089 | 10 | 1482 | 1914 | 2411 | 11541 | 806 | good | 0.1 | 0.18 | 4 | complete
HIST-0367 | new_putting_green | 10905 | 237935.1 | 14 | 20 | 20 | Oklahoma | Additional hauling required due to site conditions. | 10905 | 12 | 954 | 2125 | 2198 | 27444 | 747 | moderate | 0.15 | 0.2 | 0 | minor_scope_gap
HIST-0368 | bunker_renovation | 322 | 129713.12 | 6 | 12 | 16 | Arkansas | Crew productivity was near plan. | 0 | 0 | 0 | 0 | 6462 | 4826 | 328 | constrained | 0.075 | 0.15 | 2 | complete
HIST-0369 | drainage_renovation | 1541 | 108043.47 | 10 | 11 | 15 | West Texas | Crew productivity was near plan. | 0 | 0 | 898 | 0 | 0 | 1302 | 901 | good | 0.15 | 0.18 | 4 | complete
HIST-0370 | bunker_renovation | 1202 | 51807.13 | 8 | 9 | 11 | East Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 3358 | 4459 | 565 | good | 0.15 | 0.18 | 2 | complete
HIST-0371 | fairway_grassing | 97560 | 84377.01 | 15 | 22 | 26 | East Texas | Completed with standard site access. | 97560 | 12 | 0 | 0 | 0 | 28435 | 352 | good | 0.15 | 0.1 | 4 | complete
HIST-0372 | putting_green_renovation | 8305 | 127119.23 | 10 | 19 | 22 | East Texas | Scope change approved during construction. | 8305 | 12 | 668 | 873 | 737 | 18670 | 757 | good | 0.05 | 0.2 | 3 | complete
HIST-0373 | tee_renovation | 7382 | 54071.57 | 6 | 15 | 14 | West Texas | Unexpected subsurface conditions increased effort. | 7382 | 12 | 91 | 183 | 0 | 27906 | 502 | good | 0.15 | 0.1 | 0 | complete
HIST-0374 | putting_green_renovation | 10285 | 139813.83 | 12 | 11 | 11 | Central Texas | Scope change approved during construction. | 10285 | 10 | 659 | 1390 | 743 | 21067 | 664 | moderate | 0.05 | 0.2 | 0 | complete
HIST-0375 | drainage_renovation | 2112 | 125791.7 | 9 | 11 | 12 | Oklahoma | Utility coordination added schedule risk. | 0 | 0 | 1291 | 0 | 0 | 1721 | 1455 | constrained | 0.15 | 0.15 | 0 | complete
HIST-0376 | new_putting_green | 9360 | 140176.38 | 11 | 28 | 28 | Arkansas | Utility coordination added schedule risk. | 9360 | 6 | 914 | 1215 | 2082 | 18321 | 759 | good | 0.075 | 0.18 | 0 | complete
HIST-0377 | new_putting_green | 14458 | 145573.01 | 12 | 20 | 24 | Oklahoma | Additional hauling required due to site conditions. | 14458 | 12 | 832 | 1741 | 2269 | 22908 | 1057 | good | 0.1 | 0.1 | 4 | complete
HIST-0378 | bunker_renovation | 1055 | 64980.44 | 7 | 15 | 16 | Central Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 10963 | 2292 | 148 | good | 0.125 | 0.15 | 1 | complete
HIST-0379 | tee_renovation | 18154 | 54526.2 | 4 | 13 | 14 | East Texas | Additional hauling required due to site conditions. | 18154 | 12 | 453 | 625 | 0 | 9028 | 282 | good | 0.15 | 0.18 | 1 | minor_scope_gap
HIST-0380 | fairway_grassing | 177921 | 160073.66 | 12 | 8 | 10 | West Texas | Final quantities reconciled against field measurements. | 177921 | 12 | 0 | 0 | 0 | 35411 | 1127 | moderate | 0.15 | 0.1 | 2 | complete
HIST-0381 | putting_green_renovation | 7250 | 102201.55 | 9 | 20 | 26 | North Texas | Completed with minor quantity adjustments. | 7250 | 6 | 632 | 1633 | 25 | 6087 | 553 | moderate | 0.125 | 0.15 | 6 | complete
HIST-0382 | bunker_renovation | 769 | 109892.86 | 5 | 9 | 11 | East Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 0 | 6232 | 2957 | 147 | constrained | 0.15 | 0.12 | 0 | complete
HIST-0383 | bunker_renovation | 662 | 58408.74 | 8 | 12 | 14 | Central Texas | Completed with standard site access. | 0 | 0 | 0 | 0 | 5813 | 1016 | 121 | moderate | 0.1 | 0.15 | 2 | complete
HIST-0384 | putting_green_renovation | 7810 | 98366.69 | 7 | 21 | 18 | Central Texas | Crew productivity was near plan. | 7810 | 10 | 520 | 1194 | 1038 | 18058 | 814 | good | 0.075 | 0.12 | 0 | complete
HIST-0385 | tee_renovation | 21241 | 67493.81 | 7 | 14 | 20 | Central Texas | Crew productivity was near plan. | 21241 | 12 | 517 | 762 | 0 | 29770 | 411 | good | 0.125 | 0.1 | 6 | complete
HIST-0386 | irrigation_renovation | 7135 | 132520.43 | 13 | 12 | 9 | West Texas | Minor weather delay; scope completed. | 0 | 0 | 0 | 7135 | 0 | 7827 | 1221 | moderate | 0.05 | 0.1 | 0 | complete
HIST-0387 | tee_renovation | 17430 | 47496.21 | 7 | 8 | 10 | Arkansas | Unexpected subsurface conditions increased effort. | 17430 | 12 | 500 | 624 | 0 | 14569 | 513 | moderate | 0.15 | 0.1 | 2 | complete
HIST-0388 | drainage_renovation | 5012 | 81208.77 | 5 | 12 | 15 | West Texas | Additional hauling required due to site conditions. | 0 | 0 | 2533 | 0 | 0 | 6086 | 673 | moderate | 0.15 | 0.15 | 3 | complete
HIST-0389 | fairway_grassing | 150714 | 79269.13 | 14 | 18 | 18 | Arkansas | Completed with minor quantity adjustments. | 150714 | 12 | 0 | 0 | 0 | 15434 | 1197 | moderate | 0.1 | 0.2 | 0 | complete
HIST-0390 | bunker_renovation | 295 | 83412.33 | 5 | 15 | 15 | West Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 0 | 6916 | 4448 | 105 | good | 0.15 | 0.1 | 0 | complete
HIST-0391 | fairway_grassing | 87104 | 160524.28 | 14 | 13 | 10 | North Texas | Scope change approved during construction. | 87104 | 10 | 0 | 0 | 0 | 51815 | 526 | moderate | 0.075 | 0.15 | 0 | complete
HIST-0392 | irrigation_renovation | 6012 | 98362.69 | 6 | 17 | 19 | Arkansas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 6012 | 0 | 6374 | 1204 | constrained | 0.05 | 0.1 | 0 | complete
HIST-0393 | irrigation_renovation | 1811 | 152241.01 | 10 | 24 | 22 | Central Texas | Utility coordination added schedule risk. | 0 | 0 | 0 | 1811 | 0 | 4791 | 1618 | moderate | 0.15 | 0.18 | 0 | complete
HIST-0394 | new_putting_green | 8133 | 182444.1 | 10 | 21 | 27 | Oklahoma | Minor weather delay; scope completed. | 8133 | 12 | 983 | 2415 | 3389 | 13135 | 474 | moderate | 0.15 | 0.1 | 6 | minor_scope_gap
HIST-0395 | tee_renovation | 22914 | 50156.17 | 7 | 9 | 9 | North Texas | Minor weather delay; scope completed. | 22914 | 12 | 335 | 485 | 0 | 12794 | 227 | good | 0.125 | 0.15 | 0 | complete
HIST-0396 | bunker_renovation | 552 | 48105 | 9 | 9 | 10 | East Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 0 | 5770 | 5025 | 143 | good | 0.075 | 0.18 | 1 | complete
HIST-0397 | tee_renovation | 21698 | 83543.85 | 6 | 14 | 14 | Oklahoma | Crew productivity was near plan. | 21698 | 12 | 119 | 255 | 0 | 18076 | 123 | good | 0.15 | 0.18 | 0 | complete
HIST-0398 | bunker_renovation | 654 | 69143.26 | 9 | 8 | 8 | Arkansas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 0 | 10148 | 5355 | 247 | good | 0.1 | 0.1 | 0 | complete
HIST-0399 | tee_renovation | 23220 | 88057.37 | 4 | 14 | 18 | Central Texas | Crew productivity was near plan. | 23220 | 6 | 356 | 535 | 0 | 17363 | 153 | moderate | 0.125 | 0.18 | 4 | complete
HIST-0400 | bunker_renovation | 540 | 86963.57 | 5 | 10 | 10 | Arkansas | Completed with standard site access. | 0 | 0 | 0 | 0 | 5154 | 3846 | 527 | moderate | 0.05 | 0.12 | 0 | complete
HIST-0401 | putting_green_renovation | 5690 | 98000.5 | 11 | 14 | 15 | East Texas | Scope change approved during construction. | 5690 | 12 | 488 | 1165 | 1561 | 8208 | 349 | good | 0.125 | 0.12 | 1 | complete
HIST-0402 | fairway_grassing | 104598 | 147170.72 | 16 | 21 | 21 | Oklahoma | Minor weather delay; scope completed. | 104598 | 12 | 0 | 0 | 0 | 60594 | 1307 | good | 0.075 | 0.1 | 0 | complete
HIST-0403 | irrigation_renovation | 6718 | 85397.48 | 6 | 21 | 17 | Oklahoma | Material delivery timing affected productivity. | 0 | 0 | 0 | 6718 | 0 | 2754 | 1196 | good | 0.125 | 0.2 | 0 | complete
HIST-0404 | fairway_grassing | 202091 | 153761.42 | 14 | 10 | 13 | East Texas | Additional hauling required due to site conditions. | 202091 | 10 | 0 | 0 | 0 | 45160 | 1320 | constrained | 0.05 | 0.12 | 1 | complete
HIST-0405 | drainage_renovation | 3178 | 97594.13 | 6 | 18 | 18 | West Texas | Material delivery timing affected productivity. | 0 | 0 | 2299 | 0 | 0 | 8427 | 707 | good | 0.15 | 0.2 | 0 | complete
HIST-0406 | putting_green_renovation | 13038 | 110072.23 | 10 | 15 | 16 | Oklahoma | Minor weather delay; scope completed. | 13038 | 12 | 1180 | 1870 | 638 | 6087 | 619 | good | 0.05 | 0.1 | 1 | complete
HIST-0407 | putting_green_renovation | 7906 | 182368.7 | 10 | 23 | 28 | North Texas | Additional hauling required due to site conditions. | 7906 | 8 | 1285 | 1849 | 1217 | 13963 | 755 | constrained | 0.075 | 0.18 | 3 | complete
HIST-0408 | putting_green_renovation | 5691 | 167272.46 | 12 | 21 | 21 | Central Texas | Minor weather delay; scope completed. | 5691 | 10 | 1100 | 2079 | 36 | 20811 | 434 | moderate | 0.075 | 0.12 | 0 | complete
HIST-0409 | irrigation_renovation | 9843 | 101877.02 | 10 | 24 | 24 | North Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 9843 | 0 | 711 | 1141 | moderate | 0.1 | 0.15 | 0 | complete
HIST-0410 | putting_green_renovation | 8017 | 140722.65 | 12 | 23 | 25 | East Texas | Minor weather delay; scope completed. | 8017 | 12 | 670 | 1560 | 1766 | 14371 | 199 | good | 0.05 | 0.1 | 2 | complete
HIST-0411 | bunker_renovation | 311 | 74556.92 | 7 | 6 | 6 | West Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 0 | 4986 | 5687 | 354 | good | 0.05 | 0.12 | 0 | minor_scope_gap
HIST-0412 | bunker_renovation | 862 | 61323.3 | 9 | 10 | 10 | Oklahoma | Additional hauling required due to site conditions. | 0 | 0 | 0 | 0 | 10553 | 3741 | 486 | moderate | 0.05 | 0.12 | 0 | complete
HIST-0413 | tee_renovation | 11657 | 59726.82 | 9 | 13 | 15 | West Texas | Completed with standard site access. | 11657 | 10 | 261 | 364 | 0 | 9090 | 186 | constrained | 0.125 | 0.2 | 0 | complete
HIST-0414 | irrigation_renovation | 1941 | 81504.05 | 10 | 25 | 28 | Arkansas | Scope change approved during construction. | 0 | 0 | 0 | 1941 | 0 | 6504 | 1376 | good | 0.15 | 0.2 | 3 | complete
HIST-0415 | new_putting_green | 13140 | 190500.77 | 11 | 34 | 38 | Oklahoma | Utility coordination added schedule risk. | 13140 | 12 | 1659 | 2366 | 331 | 22152 | 592 | good | 0.125 | 0.12 | 4 | complete
HIST-0416 | tee_renovation | 9498 | 41694.47 | 4 | 7 | 7 | Central Texas | Utility coordination added schedule risk. | 9498 | 12 | 156 | 370 | 0 | 14853 | 339 | good | 0.075 | 0.12 | 0 | complete
HIST-0417 | putting_green_renovation | 9329 | 185665.38 | 7 | 11 | 13 | West Texas | Unexpected subsurface conditions increased effort. | 9329 | 12 | 700 | 1142 | 1669 | 19659 | 896 | constrained | 0.05 | 0.1 | 0 | complete
HIST-0418 | bunker_renovation | 340 | 77808.3 | 7 | 9 | 13 | West Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 7572 | 3325 | 623 | constrained | 0.05 | 0.18 | 2 | complete
HIST-0419 | putting_green_renovation | 9178 | 162105.1 | 8 | 17 | 16 | West Texas | Unexpected subsurface conditions increased effort. | 9178 | 12 | 807 | 1769 | 394 | 12956 | 888 | good | 0.075 | 0.1 | 0 | complete
HIST-0420 | tee_renovation | 22071 | 50262.5 | 7 | 8 | 7 | Arkansas | Additional hauling required due to site conditions. | 22071 | 12 | 252 | 637 | 0 | 20191 | 135 | good | 0.15 | 0.2 | 0 | complete
HIST-0421 | irrigation_renovation | 10417 | 121674.56 | 12 | 18 | 20 | Central Texas | Utility coordination added schedule risk. | 0 | 0 | 0 | 10417 | 0 | 7915 | 874 | moderate | 0.05 | 0.18 | 2 | complete
HIST-0422 | new_putting_green | 8521 | 235664.38 | 15 | 19 | 21 | Arkansas | Completed with minor quantity adjustments. | 8521 | 10 | 1053 | 1380 | 1849 | 22284 | 543 | constrained | 0.1 | 0.15 | 0 | complete
HIST-0423 | bunker_renovation | 452 | 74965.74 | 9 | 10 | 13 | Central Texas | Utility coordination added schedule risk. | 0 | 0 | 0 | 0 | 10136 | 5854 | 598 | moderate | 0.05 | 0.18 | 3 | complete
HIST-0424 | tee_renovation | 20114 | 68816.49 | 9 | 7 | 7 | Arkansas | Completed with standard site access. | 20114 | 12 | 444 | 637 | 0 | 9482 | 533 | good | 0.075 | 0.12 | 0 | complete
HIST-0425 | tee_renovation | 17195 | 76003.13 | 9 | 6 | 9 | North Texas | Unexpected subsurface conditions increased effort. | 17195 | 12 | 160 | 420 | 0 | 11551 | 418 | moderate | 0.05 | 0.15 | 3 | complete
HIST-0426 | new_putting_green | 12537 | 171292.65 | 15 | 23 | 26 | Arkansas | Minor weather delay; scope completed. | 12537 | 12 | 1056 | 1278 | 1825 | 24092 | 662 | constrained | 0.15 | 0.18 | 1 | complete
HIST-0427 | tee_renovation | 7598 | 39047.66 | 7 | 7 | 7 | North Texas | Material delivery timing affected productivity. | 7598 | 12 | 138 | 224 | 0 | 19161 | 200 | good | 0.1 | 0.15 | 0 | complete
HIST-0428 | irrigation_renovation | 7136 | 70623.45 | 8 | 15 | 11 | North Texas | Completed with minor quantity adjustments. | 0 | 0 | 0 | 7136 | 0 | 5870 | 314 | good | 0.05 | 0.18 | 0 | complete
HIST-0429 | irrigation_renovation | 3499 | 73777.84 | 13 | 22 | 22 | Arkansas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 3499 | 0 | 4412 | 775 | good | 0.075 | 0.2 | 0 | complete
HIST-0430 | bunker_renovation | 503 | 84695.1 | 9 | 10 | 10 | Central Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 6978 | 2285 | 229 | moderate | 0.125 | 0.12 | 0 | complete
HIST-0431 | tee_renovation | 17905 | 91442.46 | 9 | 11 | 11 | West Texas | Unexpected subsurface conditions increased effort. | 17905 | 12 | 271 | 618 | 0 | 9841 | 487 | good | 0.15 | 0.2 | 0 | complete
HIST-0432 | new_putting_green | 13620 | 228817.93 | 15 | 18 | 22 | North Texas | Scope change approved during construction. | 13620 | 6 | 981 | 1925 | 203 | 17475 | 527 | constrained | 0.05 | 0.12 | 2 | complete
HIST-0433 | bunker_renovation | 996 | 110225.23 | 9 | 8 | 8 | East Texas | Crew productivity was near plan. | 0 | 0 | 0 | 0 | 4697 | 4820 | 196 | good | 0.1 | 0.2 | 0 | complete
HIST-0434 | bunker_renovation | 734 | 104993.56 | 6 | 8 | 8 | North Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 6475 | 4300 | 166 | good | 0.125 | 0.12 | 0 | complete
HIST-0435 | irrigation_renovation | 7758 | 113360.78 | 12 | 13 | 14 | Central Texas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 7758 | 0 | 1855 | 1397 | moderate | 0.15 | 0.1 | 1 | complete
HIST-0436 | putting_green_renovation | 10302 | 125900.63 | 11 | 10 | 12 | Arkansas | Additional hauling required due to site conditions. | 10302 | 8 | 963 | 1292 | 458 | 8444 | 268 | moderate | 0.125 | 0.2 | 2 | complete
HIST-0437 | irrigation_renovation | 3969 | 70917.44 | 11 | 28 | 28 | North Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 3969 | 0 | 3910 | 1665 | moderate | 0.05 | 0.18 | 0 | complete
HIST-0438 | irrigation_renovation | 9414 | 142061.13 | 8 | 28 | 29 | Arkansas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 9414 | 0 | 5076 | 754 | good | 0.125 | 0.12 | 1 | complete
HIST-0439 | new_putting_green | 10139 | 218469.11 | 12 | 33 | 41 | Oklahoma | Completed with standard site access. | 10139 | 12 | 422 | 1023 | 1740 | 22133 | 468 | constrained | 0.125 | 0.18 | 6 | minor_scope_gap
HIST-0440 | irrigation_renovation | 9943 | 73945.14 | 6 | 24 | 28 | Oklahoma | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 9943 | 0 | 2552 | 1138 | good | 0.1 | 0.1 | 4 | complete
HIST-0441 | tee_renovation | 9961 | 82811.67 | 7 | 10 | 12 | East Texas | Material delivery timing affected productivity. | 9961 | 12 | 141 | 395 | 0 | 26116 | 147 | good | 0.05 | 0.12 | 2 | minor_scope_gap
HIST-0442 | new_putting_green | 11650 | 143516.6 | 8 | 18 | 15 | Central Texas | Completed with minor quantity adjustments. | 11650 | 12 | 601 | 1559 | 553 | 21784 | 581 | moderate | 0.05 | 0.15 | 0 | complete
HIST-0443 | putting_green_renovation | 6423 | 160664.2 | 10 | 22 | 20 | Oklahoma | Completed with standard site access. | 6423 | 12 | 614 | 1184 | 570 | 21470 | 651 | good | 0.125 | 0.12 | 0 | complete
HIST-0444 | putting_green_renovation | 8685 | 123178.75 | 9 | 14 | 16 | Oklahoma | Additional hauling required due to site conditions. | 8685 | 12 | 1271 | 1750 | 1153 | 7958 | 864 | good | 0.15 | 0.2 | 2 | complete
HIST-0445 | putting_green_renovation | 11048 | 159254.93 | 12 | 13 | 16 | Central Texas | Final quantities reconciled against field measurements. | 11048 | 12 | 1002 | 1867 | 383 | 19675 | 483 | constrained | 0.125 | 0.12 | 1 | complete
HIST-0446 | bunker_renovation | 1051 | 42622.45 | 9 | 6 | 6 | Central Texas | Completed with standard site access. | 0 | 0 | 0 | 0 | 6812 | 3224 | 599 | good | 0.15 | 0.15 | 0 | complete
HIST-0447 | bunker_renovation | 458 | 100328.28 | 9 | 14 | 18 | Arkansas | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 0 | 9730 | 5697 | 178 | constrained | 0.05 | 0.1 | 2 | complete
HIST-0448 | bunker_renovation | 1218 | 51099.7 | 5 | 7 | 8 | North Texas | Minor weather delay; scope completed. | 0 | 0 | 0 | 0 | 10683 | 1232 | 457 | good | 0.1 | 0.1 | 1 | complete
HIST-0449 | putting_green_renovation | 11543 | 94893.62 | 8 | 13 | 14 | North Texas | Unexpected subsurface conditions increased effort. | 11543 | 12 | 722 | 1869 | 1286 | 8046 | 818 | good | 0.15 | 0.12 | 1 | complete
HIST-0450 | tee_renovation | 10632 | 66856.2 | 6 | 9 | 9 | West Texas | Minor weather delay; scope completed. | 10632 | 12 | 574 | 743 | 0 | 11642 | 481 | good | 0.15 | 0.15 | 0 | complete
HIST-0451 | new_putting_green | 13675 | 245650.13 | 8 | 18 | 19 | East Texas | Completed with minor quantity adjustments. | 13675 | 12 | 1120 | 1376 | 2371 | 24131 | 799 | constrained | 0.05 | 0.1 | 0 | complete
HIST-0452 | bunker_renovation | 1189 | 67564.87 | 10 | 11 | 11 | East Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 0 | 10829 | 2509 | 110 | good | 0.15 | 0.15 | 0 | complete
HIST-0453 | tee_renovation | 14714 | 78589.59 | 9 | 14 | 12 | Central Texas | Scope change approved during construction. | 14714 | 12 | 132 | 232 | 0 | 25618 | 161 | good | 0.075 | 0.18 | 0 | complete
HIST-0454 | irrigation_renovation | 9004 | 161051.02 | 6 | 18 | 19 | North Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 9004 | 0 | 607 | 702 | constrained | 0.125 | 0.12 | 0 | complete
HIST-0455 | bunker_renovation | 295 | 77209.09 | 7 | 6 | 12 | West Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 4614 | 2914 | 534 | moderate | 0.05 | 0.15 | 6 | complete
HIST-0456 | tee_renovation | 15708 | 65661.67 | 7 | 7 | 7 | Central Texas | Completed with minor quantity adjustments. | 15708 | 8 | 304 | 647 | 0 | 23023 | 159 | moderate | 0.1 | 0.1 | 0 | complete
HIST-0457 | bunker_renovation | 829 | 93095.48 | 7 | 9 | 15 | Central Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 3465 | 1373 | 561 | good | 0.125 | 0.2 | 6 | complete
HIST-0458 | tee_renovation | 23358 | 48022.96 | 4 | 10 | 13 | Central Texas | Material delivery timing affected productivity. | 23358 | 12 | 334 | 410 | 0 | 14795 | 236 | moderate | 0.15 | 0.12 | 3 | complete
HIST-0459 | irrigation_renovation | 3651 | 105031.23 | 13 | 18 | 23 | North Texas | Additional hauling required due to site conditions. | 0 | 0 | 0 | 3651 | 0 | 556 | 448 | constrained | 0.15 | 0.15 | 3 | complete
HIST-0460 | irrigation_renovation | 7101 | 118843.6 | 11 | 26 | 29 | Arkansas | Scope change approved during construction. | 0 | 0 | 0 | 7101 | 0 | 3065 | 1053 | constrained | 0.05 | 0.12 | 1 | complete
HIST-0461 | tee_renovation | 14536 | 76854.86 | 7 | 6 | 4 | Oklahoma | Utility coordination added schedule risk. | 14536 | 12 | 131 | 293 | 0 | 28699 | 252 | moderate | 0.15 | 0.12 | 0 | complete
HIST-0462 | putting_green_renovation | 7329 | 94469.27 | 9 | 13 | 19 | East Texas | Minor weather delay; scope completed. | 7329 | 8 | 668 | 1762 | 1455 | 5595 | 458 | constrained | 0.15 | 0.2 | 4 | complete
HIST-0463 | fairway_grassing | 49200 | 188685.97 | 9 | 16 | 18 | Arkansas | Completed with minor quantity adjustments. | 49200 | 12 | 0 | 0 | 0 | 50598 | 1713 | constrained | 0.15 | 0.1 | 0 | complete
HIST-0464 | irrigation_renovation | 9574 | 152070.19 | 9 | 19 | 17 | Oklahoma | Scope change approved during construction. | 0 | 0 | 0 | 9574 | 0 | 6472 | 1233 | moderate | 0.05 | 0.18 | 0 | complete
HIST-0465 | tee_renovation | 23883 | 49436.71 | 5 | 12 | 12 | Oklahoma | Scope change approved during construction. | 23883 | 6 | 482 | 719 | 0 | 29124 | 293 | moderate | 0.15 | 0.1 | 0 | complete
HIST-0466 | drainage_renovation | 5868 | 80145.17 | 12 | 19 | 25 | North Texas | Completed with minor quantity adjustments. | 0 | 0 | 3983 | 0 | 0 | 8922 | 1030 | good | 0.1 | 0.15 | 6 | complete
HIST-0467 | bunker_renovation | 1085 | 107292.81 | 8 | 9 | 7 | Central Texas | Scope change approved during construction. | 0 | 0 | 0 | 0 | 5416 | 4571 | 598 | moderate | 0.125 | 0.15 | 0 | minor_scope_gap
HIST-0468 | new_putting_green | 13531 | 242725.18 | 14 | 25 | 24 | Oklahoma | Completed with standard site access. | 13531 | 8 | 742 | 885 | 1202 | 14393 | 642 | good | 0.1 | 0.15 | 0 | complete
HIST-0469 | bunker_renovation | 443 | 78704.89 | 10 | 11 | 13 | North Texas | Crew productivity was near plan. | 0 | 0 | 0 | 0 | 9364 | 1316 | 500 | moderate | 0.15 | 0.1 | 2 | complete
HIST-0470 | tee_renovation | 16565 | 51191.26 | 8 | 11 | 15 | Arkansas | Utility coordination added schedule risk. | 16565 | 12 | 546 | 655 | 0 | 14874 | 489 | good | 0.125 | 0.18 | 4 | complete
HIST-0471 | putting_green_renovation | 10834 | 143348.06 | 7 | 20 | 18 | Central Texas | Completed with minor quantity adjustments. | 10834 | 12 | 889 | 1376 | 1200 | 18141 | 838 | constrained | 0.15 | 0.2 | 0 | complete
HIST-0472 | irrigation_renovation | 8237 | 89150.05 | 9 | 25 | 27 | Arkansas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 8237 | 0 | 1931 | 641 | moderate | 0.075 | 0.15 | 2 | complete
HIST-0473 | fairway_grassing | 86723 | 94443.85 | 8 | 25 | 27 | Arkansas | Scope change approved during construction. | 86723 | 8 | 0 | 0 | 0 | 24186 | 731 | constrained | 0.075 | 0.18 | 0 | complete
HIST-0474 | irrigation_renovation | 9628 | 131242.91 | 9 | 21 | 21 | Oklahoma | Crew productivity was near plan. | 0 | 0 | 0 | 9628 | 0 | 5132 | 1180 | good | 0.075 | 0.18 | 0 | complete
HIST-0475 | irrigation_renovation | 4477 | 118626.59 | 12 | 19 | 18 | North Texas | Completed with standard site access. | 0 | 0 | 0 | 4477 | 0 | 669 | 863 | good | 0.15 | 0.12 | 0 | complete
HIST-0476 | irrigation_renovation | 6692 | 143055.64 | 11 | 19 | 17 | Central Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 6692 | 0 | 1877 | 1065 | good | 0.15 | 0.12 | 0 | complete
HIST-0477 | putting_green_renovation | 9349 | 112600.91 | 10 | 22 | 21 | East Texas | Scope change approved during construction. | 9349 | 12 | 977 | 1329 | 1622 | 20840 | 435 | good | 0.125 | 0.15 | 0 | complete
HIST-0478 | drainage_renovation | 5656 | 104559.97 | 8 | 18 | 21 | North Texas | Additional hauling required due to site conditions. | 0 | 0 | 2234 | 0 | 0 | 1473 | 587 | good | 0.05 | 0.12 | 3 | complete
HIST-0479 | bunker_renovation | 832 | 82686.28 | 10 | 14 | 16 | West Texas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 7412 | 2069 | 538 | moderate | 0.075 | 0.15 | 2 | complete
HIST-0480 | tee_renovation | 8665 | 66294.75 | 5 | 8 | 6 | Central Texas | Utility coordination added schedule risk. | 8665 | 12 | 105 | 266 | 0 | 15570 | 292 | moderate | 0.05 | 0.1 | 0 | complete
HIST-0481 | putting_green_renovation | 7777 | 153050.33 | 9 | 14 | 17 | Oklahoma | Material delivery timing affected productivity. | 7777 | 8 | 579 | 736 | 798 | 17220 | 601 | moderate | 0.05 | 0.18 | 3 | complete
HIST-0482 | putting_green_renovation | 8305 | 153389.87 | 10 | 17 | 17 | East Texas | Completed with standard site access. | 8305 | 12 | 928 | 1492 | 1510 | 5631 | 742 | moderate | 0.125 | 0.15 | 0 | complete
HIST-0483 | drainage_renovation | 5666 | 82615.44 | 7 | 11 | 13 | East Texas | Minor weather delay; scope completed. | 0 | 0 | 3700 | 0 | 0 | 3195 | 542 | moderate | 0.075 | 0.18 | 2 | complete
HIST-0484 | fairway_grassing | 178634 | 129668.06 | 12 | 12 | 11 | Arkansas | Completed with standard site access. | 178634 | 8 | 0 | 0 | 0 | 19215 | 1272 | good | 0.075 | 0.1 | 0 | complete
HIST-0485 | irrigation_renovation | 4397 | 145758.8 | 12 | 28 | 32 | Oklahoma | Crew productivity was near plan. | 0 | 0 | 0 | 4397 | 0 | 1859 | 986 | constrained | 0.125 | 0.12 | 2 | complete
HIST-0486 | fairway_grassing | 124439 | 181734.43 | 10 | 13 | 14 | Oklahoma | Completed with standard site access. | 124439 | 12 | 0 | 0 | 0 | 20862 | 1648 | constrained | 0.1 | 0.2 | 0 | complete
HIST-0487 | irrigation_renovation | 5363 | 122873.62 | 12 | 20 | 23 | Central Texas | Scope change approved during construction. | 0 | 0 | 0 | 5363 | 0 | 7999 | 1285 | good | 0.1 | 0.18 | 3 | complete
HIST-0488 | drainage_renovation | 4463 | 47977.54 | 5 | 13 | 15 | Arkansas | Crew productivity was near plan. | 0 | 0 | 2253 | 0 | 0 | 771 | 759 | good | 0.15 | 0.1 | 2 | complete
HIST-0489 | drainage_renovation | 4929 | 94020.19 | 8 | 10 | 14 | West Texas | Material delivery timing affected productivity. | 0 | 0 | 3756 | 0 | 0 | 7663 | 333 | good | 0.1 | 0.1 | 4 | complete
HIST-0490 | new_putting_green | 10050 | 150055.72 | 12 | 31 | 33 | Central Texas | Minor weather delay; scope completed. | 10050 | 12 | 1922 | 2537 | 1192 | 18383 | 629 | good | 0.075 | 0.12 | 2 | complete
HIST-0491 | tee_renovation | 22676 | 69334.22 | 4 | 11 | 13 | Arkansas | Additional hauling required due to site conditions. | 22676 | 12 | 423 | 512 | 0 | 10746 | 470 | moderate | 0.1 | 0.15 | 2 | complete
HIST-0492 | drainage_renovation | 3166 | 89466.67 | 11 | 15 | 16 | North Texas | Minor weather delay; scope completed. | 0 | 0 | 2377 | 0 | 0 | 5734 | 480 | moderate | 0.075 | 0.1 | 1 | complete
HIST-0493 | bunker_renovation | 1206 | 80403.23 | 10 | 16 | 13 | Arkansas | Unexpected subsurface conditions increased effort. | 0 | 0 | 0 | 0 | 7449 | 5658 | 140 | good | 0.15 | 0.1 | 0 | complete
HIST-0494 | putting_green_renovation | 10416 | 165882.62 | 8 | 22 | 19 | North Texas | Additional hauling required due to site conditions. | 10416 | 12 | 332 | 667 | 185 | 19762 | 727 | moderate | 0.15 | 0.18 | 0 | complete
HIST-0495 | irrigation_renovation | 9619 | 97599.87 | 8 | 14 | 11 | Oklahoma | Final quantities reconciled against field measurements. | 0 | 0 | 0 | 9619 | 0 | 1850 | 1000 | moderate | 0.15 | 0.1 | 0 | complete
HIST-0496 | drainage_renovation | 1459 | 110868.67 | 11 | 13 | 12 | Central Texas | Additional hauling required due to site conditions. | 0 | 0 | 589 | 0 | 0 | 2486 | 1499 | good | 0.15 | 0.1 | 0 | complete
HIST-0497 | irrigation_renovation | 4026 | 142752.91 | 6 | 12 | 11 | Oklahoma | Completed with minor quantity adjustments. | 0 | 0 | 0 | 4026 | 0 | 3668 | 764 | moderate | 0.125 | 0.2 | 0 | complete
HIST-0498 | new_putting_green | 13341 | 228165.6 | 13 | 30 | 31 | Central Texas | Material delivery timing affected productivity. | 13341 | 8 | 1021 | 1278 | 579 | 11036 | 764 | good | 0.15 | 0.18 | 1 | complete
HIST-0499 | irrigation_renovation | 6602 | 87773.61 | 9 | 10 | 8 | East Texas | Material delivery timing affected productivity. | 0 | 0 | 0 | 6602 | 0 | 1178 | 1081 | good | 0.05 | 0.2 | 0 | complete
HIST-0500 | putting_green_renovation | 11997 | 164585.99 | 8 | 18 | 22 | Central Texas | Final quantities reconciled against field measurements. | 11997 | 12 | 357 | 852 | 1779 | 9775 | 286 | moderate | 0.1 | 0.2 | 4 | complete

## Estimation_Rules
rule_id | rule_name | formula_or_logic | output_unit | notes
R-001 | Rootzone volume | area_sqft * depth_in / 324 | bulk_cy | Use only when green/tee area and depth are specified.
R-002 | Material order quantity | calculated_quantity * (1 + waste_factor) | material unit | Round up to supplier packaging or truckload where applicable.
R-003 | Labor hours | installed_quantity / productivity_per_labor_hour | labor_hour | Use the productivity unit matching the work quantity.
R-004 | Labor cost | labor_hours * loaded_hourly_rate | USD | Loaded rate is synthetic and includes assumed burden.
R-005 | Material line total | order_quantity * unit_cost | USD | Record base quantity and waste quantity separately.
R-006 | Bid subtotal | materials + labor + equipment + subcontractors | USD | Avoid double-counting labor inside unit rates.
R-007 | Contingency | direct_cost_subtotal * contingency_pct | USD | Use higher allowance when scope or site conditions are uncertain.
R-008 | Overhead and profit | (direct_cost_subtotal + contingency) * markup_pct | USD | Keep markup assumptions visible in the estimate.
R-009 | Clarification gate | if required dimensions/specifications are missing, request clarification | decision | Do not silently invent design-critical dimensions.
R-010 | Historical calibration | compare scope, region, access, and project type with similar completed projects | decision | Use comparable records; do not copy historical totals blindly.
R-011 | Crew size estimate | labor_hours / productive_hours_per_person_per_day / target_duration_days | people | Round up and apply task-specific minimum crew and supervision rules.
R-012 | Schedule risk | actual_duration_days - planned_duration_days | days | Use historical variance to inform schedule contingency.
R-013 | Data quality gate | if data_quality indicates scope gap, flag estimate for review | decision | Do not present low-confidence estimates as final.

## Labor_Productivity
labor_code | role | work_type | rate_usd_per_hour_loaded | illustrative_productivity_rate | productivity_unit | crew_role | assumption_note
LAB-001 | General laborer | site_prep | 29 | 55 | CY/hour | worker | Synthetic planning assumption; validate with contractor history.
LAB-002 | Equipment operator | earthwork | 42 | 32 | CY/hour | operator | Synthetic planning assumption; validate with contractor history.
LAB-003 | Irrigation technician | irrigation | 38 | 110 | LF/hour | technician | Synthetic planning assumption; validate with contractor history.
LAB-004 | Drainage installer | drainage | 35 | 85 | LF/hour | installer | Synthetic planning assumption; validate with contractor history.
LAB-005 | Finish shaper | green_construction | 39 | 900 | SF/hour | specialist | Synthetic planning assumption; validate with contractor history.
LAB-006 | Sod installer | turf | 31 | 1200 | SF/hour | installer | Synthetic planning assumption; validate with contractor history.
LAB-007 | Bunker installer | bunker | 34 | 450 | SF/hour | installer | Synthetic planning assumption; validate with contractor history.
LAB-008 | Foreman | supervision | 48 |  | crew supervision | supervisor | Synthetic planning assumption; validate with contractor history.

## Sample_Bid_Lines
project_id | line_item | unit | order_quantity | unit_cost_usd | extended_material_cost_usd | assumption
GC-1001 | USGA rootzone mix | bulk_cy | 345 | 118 | 40710 | Area × depth ÷ 324; includes catalog waste and rounds up to 5 CY.
GC-1001 | Perforated HDPE drainage pipe, 4 in | lf | 1313 | 2.85 | 3742.05 | Measured length plus 5% waste.
GC-1001 | PVC irrigation pipe, 2 in | lf | 945 | 2.35 | 2220.75 | Measured length plus 5% waste; confirm pipe sizing.
GC-1001 | Bermudagrass sod | sqft | 12840 | 0.48 | 6163.2 | Measured area plus 7% waste.
GC-1002 | Perforated HDPE drainage pipe, 4 in | lf | 819 | 2.85 | 2334.15 | Measured length plus 5% waste.
GC-1002 | PVC irrigation pipe, 2 in | lf | 189 | 2.35 | 444.15 | Measured length plus 5% waste; confirm pipe sizing.
GC-1002 | Bermudagrass sod | sqft | 2568 | 0.48 | 1232.64 | Measured area plus 7% waste.
GC-1003 | PVC irrigation pipe, 2 in | lf | 7140 | 2.35 | 16779 | Measured length plus 5% waste; confirm pipe sizing.
GC-1003 | Bermudagrass sod | sqft | 3745 | 0.48 | 1797.6 | Measured area plus 7% waste.
GC-1004 | USGA rootzone mix | bulk_cy | 440 | 118 | 51920 | Area × depth ÷ 324; includes catalog waste and rounds up to 5 CY.
GC-1004 | Perforated HDPE drainage pipe, 4 in | lf | 1680 | 2.85 | 4788 | Measured length plus 5% waste.
GC-1004 | PVC irrigation pipe, 2 in | lf | 1260 | 2.35 | 2961 | Measured length plus 5% waste; confirm pipe sizing.
GC-1004 | Bermudagrass sod | sqft | 17120 | 0.48 | 8217.6 | Measured area plus 7% waste.
GC-1005 | Perforated HDPE drainage pipe, 4 in | lf | 441 | 2.85 | 1256.85 | Measured length plus 5% waste.
GC-1005 | PVC irrigation pipe, 2 in | lf | 683 | 2.35 | 1605.05 | Measured length plus 5% waste; confirm pipe sizing.
GC-1005 | Bermudagrass sod | sqft | 19795 | 0.48 | 9501.6 | Measured area plus 7% waste.
GC-1006 | PVC irrigation pipe, 2 in | lf | 1260 | 2.35 | 2961 | Measured length plus 5% waste; confirm pipe sizing.
GC-1006 | Bermudagrass sod | sqft | 44940 | 0.48 | 21571.2 | Measured area plus 7% waste.
GC-1007 | Perforated HDPE drainage pipe, 4 in | lf | 4410 | 2.85 | 12568.5 | Measured length plus 5% waste.
GC-1007 | Bermudagrass sod | sqft | 2568 | 0.48 | 1232.64 | Measured area plus 7% waste.
GC-1008 | USGA rootzone mix | bulk_cy | 505 | 118 | 59590 | Area × depth ÷ 324; includes catalog waste and rounds up to 5 CY.
GC-1008 | Perforated HDPE drainage pipe, 4 in | lf | 1943 | 2.85 | 5537.55 | Measured length plus 5% waste.
GC-1008 | PVC irrigation pipe, 2 in | lf | 1365 | 2.35 | 3207.75 | Measured length plus 5% waste; confirm pipe sizing.
GC-1008 | Bermudagrass sod | sqft | 19795 | 0.48 | 9501.6 | Measured area plus 7% waste.
GC-1009 | Perforated HDPE drainage pipe, 4 in | lf | 987 | 2.85 | 2812.95 | Measured length plus 5% waste.
GC-1009 | PVC irrigation pipe, 2 in | lf | 252 | 2.35 | 592.2 | Measured length plus 5% waste; confirm pipe sizing.
GC-1009 | Bermudagrass sod | sqft | 3745 | 0.48 | 1797.6 | Measured area plus 7% waste.
GC-1010 | PVC irrigation pipe, 2 in | lf | 8610 | 2.35 | 20233.5 | Measured length plus 5% waste; confirm pipe sizing.
GC-1010 | Bermudagrass sod | sqft | 6634 | 0.48 | 3184.32 | Measured area plus 7% waste.
GC-1011 | USGA rootzone mix | bulk_cy | 295 | 118 | 34810 | Area × depth ÷ 324; includes catalog waste and rounds up to 5 CY.
GC-1011 | Perforated HDPE drainage pipe, 4 in | lf | 483 | 2.85 | 1376.55 | Measured length plus 5% waste.
GC-1011 | PVC irrigation pipe, 2 in | lf | 756 | 2.35 | 1776.6 | Measured length plus 5% waste; confirm pipe sizing.
GC-1011 | Bermudagrass sod | sqft | 22470 | 0.48 | 10785.6 | Measured area plus 7% waste.
GC-1012 | USGA rootzone mix | bulk_cy | 385 | 118 | 45430 | Area × depth ÷ 324; includes catalog waste and rounds up to 5 CY.
GC-1012 | Perforated HDPE drainage pipe, 4 in | lf | 1491 | 2.85 | 4249.35 | Measured length plus 5% waste.
GC-1012 | PVC irrigation pipe, 2 in | lf | 473 | 2.35 | 1111.55 | Measured length plus 5% waste; confirm pipe sizing.
GC-1012 | Bermudagrass sod | sqft | 15515 | 0.48 | 7447.2 | Measured area plus 7% waste.
GC-1013 | PVC irrigation pipe, 2 in | lf | 683 | 2.35 | 1605.05 | Measured length plus 5% waste; confirm pipe sizing.
GC-1013 | Bermudagrass sod | sqft | 58850 | 0.48 | 28248 | Measured area plus 7% waste.
GC-1014 | Perforated HDPE drainage pipe, 4 in | lf | 5460 | 2.85 | 15561 | Measured length plus 5% waste.
GC-1014 | Bermudagrass sod | sqft | 7704 | 0.48 | 3697.92 | Measured area plus 7% waste.
GC-1015 | USGA rootzone mix | bulk_cy | 360 | 118 | 42480 | Area × depth ÷ 324; includes catalog waste and rounds up to 5 CY.
GC-1015 | Perforated HDPE drainage pipe, 4 in | lf | 1239 | 2.85 | 3531.15 | Measured length plus 5% waste.
GC-1015 | PVC irrigation pipe, 2 in | lf | 1029 | 2.35 | 2418.15 | Measured length plus 5% waste; confirm pipe sizing.
GC-1015 | Bermudagrass sod | sqft | 14445 | 0.48 | 6933.6 | Measured area plus 7% waste.

## Project_Type_Ranges
project_type | illustrative_low_cost_usd | illustrative_high_cost_usd | min_crew_size | max_crew_size | min_planned_days | max_planned_days | notes
putting_green_renovation | 85000 | 170000 | 6 | 12 | 10 | 23 | Synthetic ranges for test generation; not market quotes.
bunker_renovation | 42000 | 115000 | 5 | 10 | 6 | 16 | Synthetic ranges for test generation; not market quotes.
irrigation_renovation | 60000 | 155000 | 6 | 13 | 10 | 28 | Synthetic ranges for test generation; not market quotes.
new_putting_green | 135000 | 260000 | 8 | 15 | 17 | 34 | Synthetic ranges for test generation; not market quotes.
tee_renovation | 40000 | 95000 | 4 | 9 | 6 | 15 | Synthetic ranges for test generation; not market quotes.
fairway_grassing | 65000 | 180000 | 7 | 16 | 8 | 25 | Synthetic ranges for test generation; not market quotes.
drainage_renovation | 45000 | 135000 | 5 | 12 | 8 | 22 | Synthetic ranges for test generation; not market quotes.